## Rename
Example Frontier Production System Cost and Revenue
Year ---> | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 |  |  |  | 2032 |  |  |  | 2033 |  |  |  | 2034 |  |  |  | 2035 |  |  |  | 2036 |  |  |  | 2037 |  |  |  | 2038 |  |  |  | 2039 |  |  |  | 2040 |  |  |  | 2041 |  |  |  | 2042 |  |  |  | 2043 |  |  |  | 2044 |  |  |  | 2045 |  |  |  | 2046 |  |  |  | 2047 |  |  |  | 2048 |  |  |  | 2049 |  |  |  | 2050 |  |  |  | 2051 |  |  |  | 2052
Activity | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Discovery Well
1st Appraisal Well and Sidetrack
1st Keeper Well and Sidetrack |  |  |  | 76.5 | 76.5 | 25.5
2nd Keeper Well and Sidetrack | [6 empty] | 76.5 | 76.5 | 25.5
Drill 3rd Well to 14" Casing | [9 empty] | 76.5
Drill 4th Well to 14" Casing | [10 empty] | 76.5
Drill 5th Well to 14" Casing | [11 empty] | 76.5
Pre-FEED and FEED | 2 | 5 | 5
FID (for APS deployment) |  |  |  | 5 | 5
Fab and Delivery |  |  |  |  | 125 | 100 | 100 | 100 | 100 | 100 | 100
Install, Commission Facility | [11 empty] | 20 | 20 | 20 | 10
Complete 1st Keeper | [15 empty] | 40.5 | 5 | [11 empty] | 40.5 | 40.5 | [7 empty] | 40.5 | [8 empty] | 40.5 | [10 empty] | 40.5 | 40.5 | [6 empty] | 40.5 | 40.5 | [7 empty] | 40.5 | [12 empty] | 40.5 | [10 empty] | 40.5
Complete 2nd Keeper | [16 empty] | 40.5 | 5 | [23 empty] | 40.5 | [31 empty] | 40.5 | [6 empty] | 40.5 | 40.5 | [11 empty] | 40.5 | 40.5 | [7 empty] | 40.5
Drill 3rd Well | [18 empty] | 40.5 | [31 empty] | 40.5 | 40.5
Complete 3rd Well | [19 empty] | 40.5 | 40.5 | [10 empty] | 40.5 | 40.5 | [5 empty] | 40.5 | [22 empty] | 40.5 | 40.5 | [6 empty] | 40.5 | [16 empty] | 40.5 |  |  |  |  | 40.5 | 40.5 | [6 empty] | 40.5
Drill 4th Well | [21 empty] | 40.5 | [83 empty] | 40.5 |  |  |  |  | 40.5 | 40.5
Complete 4th Well | [22 empty] | 40.5 | 40.5 | [18 empty] | 40.5 | [9 empty] | 40.5 | 40.5 | [16 empty] | 40.5 | [6 empty] | 40.5 |  |  |  |  | 40.5 | 40.5 | [22 empty] | 40.5 | [6 empty] | 40.5 | 40.5
Drill 5th Well | [24 empty] | 40.5
Complete 5th Well | [25 empty] | 40.5 | 40.5 | [18 empty] | 40.5 | [8 empty] | 40.5 | 40.5 | [20 empty] | 40.5 | [7 empty] | 40.5 | 40.5 | [17 empty] | 40.5 | [11 empty] | 40.5 | 40.5
Produce
Total | 2 | 5 | 5 | 81.5 | 206.5 | 125.5 | 176.5 | 176.5 | 125.5 | 176.5 | 176.5 | 96.5 | 20 | 20 | 10 | 40.5 | 45.5 | 5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 0 | 40.5 | 40.5 | 0 | 40.5 | 40.5 | 0 | 0 | 0 | 0 | 40.5 | 40.5 | 0 | 0 | 40.5 | 40.5 | 0 | 0 | 40.5 | 40.5 | 0 | 0 | 0 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 0 | 40.5 | 40.5 | 0 | 0 | 40.5 | 40.5 | 0 | 0 | 40.5 | 40.5 | 0 | 0 | 40.5 | 40.5 | 0 | 0 | 40.5 | 40.5 | 0 | 40.5 | 40.5 | 0 | 0 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 0 | 0 | 0 | 40.5 | 40.5 | 40.5 | 40.5 | 0 | 0 | 0 | 40.5 | 40.5 | 0 | 0 | 40.5 | 40.5 | 0 | 40.5 | 40.5 | 0 | 0 | 0 | 40.5 | 40.5 | 0 | 40.5 | 40.5 | 40.5 | 40.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | [17 empty] | 9000 | 8562.5 | 8146.2674 | 7750.2683 | 7373.5191 | 7015.0841 | 6674.0731 | 6349.639 | 6040.976 | 5747.3174 | 0 | 0 | 0 | 15000 | 14270.8333 | 13577.1123 | 12917.1138 | 12289.1985 | 11691.8069 | 11123.4552 | 10582.7317 | 10068.2933 | 9578.8624 | 9113.2233 | 8670.2193 | 8248.7503 | 7847.7694 | 7466.2806 | 7103.3364 | 6758.0354 | 6429.5198 | 6116.9737 | 5819.6208 | 5536.7225 | 5267.5763 | 5011.5136 | 4767.8983 | 4536.1255 | 4315.6194 | 4105.8323 | 0 | 0 | 5000 | 4756.9444 | 4525.7041 | 4305.7046 | 4096.3995 | 3897.269 | 0 | 0 | 17500 | 16649.3056 | 15839.9643 | 15069.966 | 14337.3983 | 13640.4414 | 12977.3644 | 12665.9076 | 12361.9259 | 12065.2396 | 11775.6739 | 11493.0577 | 10934.3674 | 10402.8357 | 9897.1423 | 9416.0312 | 8958.3074 | 8522.8342 | 8108.5297 | 7714.3651 | 7339.3612 | 6982.5867 | 6643.1554 | 6320.2243 | 6012.9911 | 5720.6929 | 0 | 0 | 15000 | 14270.8333 | 13577.1123 | 12917.1138 | 12289.1985 | 11691.8069 | 11123.4552 | 10582.7317 | 10068.2933 | 9578.8624 | 9113.2233 | 8670.2193 | 8248.7503 | 7847.7694 | 7466.2806 | 7103.3364 | 6758.0354 | 6429.5198 | 6116.9737 | 5819.6208 | 5536.7225 | 5267.5763 | 5011.5136 | 4767.8983 | 4536.1255 | 4315.6194 | 4105.8323 | 3906.2433 | 3716.3564
2 | [18 empty] | 15000 | 14270.8333 | 13577.1123 | 12917.1138 | 12289.1985 | 11691.8069 | 11123.4552 | 10582.7317 | 10068.2933 | 9578.8624 | 9113.2233 | 8670.2193 | 8248.7503 | 7847.7694 | 7466.2806 | 7103.3364 | 6758.0354 | 6429.5198 | 6116.9737 | 5819.6208 | 5536.7225 | 5267.5763 | 5011.5136 | 4767.8983 | 4536.1255 | 4315.6194 | 4105.8323 | 3906.2433 | 3716.3564 | 3535.7002 | 3363.8259 | 3200.3066 | 0 | 0 | 15000 | 14270.8333 | 13577.1123 | 12917.1138 | 12289.1985 | 11691.8069 | 11123.4552 | 10582.7317 | 10068.2933 | 9578.8624 | 9113.2233 | 8670.2193 | 8248.7503 | 7847.7694 | 7466.2806 | 7103.3364 | 6758.0354 | 6429.5198 | 6116.9737 | 5819.6208 | 5536.7225 | 5267.5763 | 5011.5136 | 4767.8983 | 4536.1255 | 4315.6194 | 4105.8323 | 3906.2433 | 0 | 0 | 15000 | 14270.8333 | 13577.1123 | 12917.1138 | 12289.1985 | 11691.8069 | 11123.4552 | 10582.7317 | 10068.2933 | 9578.8624 | 9113.2233 | 8670.2193 | 8248.7503 | 7847.7694 | 7466.2806 | 7103.3364 | 6758.0354 | 6429.5198 | 6116.9737 | 5819.6208 | 5536.7225 | 5267.5763 | 5011.5136 | 4767.8983 | 4536.1255 | 4315.6194 | 4105.8323 | 3906.2433 | 0 | 0 | 15000 | 14270.8333 | 13577.1123 | 12917.1138 | 12289.1985 | 11691.8069 | 11123.4552 | 10582.7317 | 10068.2933 | 9578.8624 | 9113.2233 | 8670.2193
3 | [20 empty] | 9000 | 8562.5 | 8146.2674 | 7750.2683 | 7373.5191 | 7015.0841 | 6674.0731 | 6349.639 | 6040.976 | 5747.3174 | 0 | 0 | 0 | 15000 | 14270.8333 | 13577.1123 | 12917.1138 | 12289.1985 | 11691.8069 | 11123.4552 | 10582.7317 | 10068.2933 | 9578.8624 | 9113.2233 | 8670.2193 | 8248.7503 | 7847.7694 | 7466.2806 | 7103.3364 | 6758.0354 | 6429.5198 | 6116.9737 | 5819.6208 | 5536.7225 | 5267.5763 | 5011.5136 | 4767.8983 | 4536.1255 | 4315.6194 | 4105.8323 | 3906.2433 | 0 | 0 | 15000 | 14270.8333 | 13577.1123 | 12917.1138 | 12289.1985 | 11691.8069 | 11123.4552 | 10582.7317 | 10068.2933 | 9578.8624 | 9113.2233 | 8670.2193 | 8248.7503 | 7847.7694 | 7466.2806 | 7103.3364 | 6758.0354 | 6429.5198 | 6116.9737 | 5819.6208 | 5536.7225 | 5267.5763 | 5011.5136 | 4767.8983 | 4536.1255 | 4315.6194 | 4105.8323 | 3906.2433 | 0 | 0 | 18000 | 17125 | 16292.5347 | 15500.5365 | 14747.0382 | 14030.1683 | 13348.1462 | 12699.278 | 12081.952 | 11494.6349 | 10935.8679 | 10404.2632 | 9898.5004 | 9417.3233 | 8959.5368 | 8524.0037 | 8109.6424 | 7715.4237 | 7340.3684 | 6983.5449 | 6644.067 | 6321.0916 | 6013.8163 | 5721.478 | 5443.3506 | 5178.7433 | 4926.9988 | 4687.4919 | 4459.6277 | 4242.8403 | 4036.5911
4 | [23 empty] | 15000 | 14270.8333 | 13577.1123 | 12917.1138 | 12289.1985 | 11691.8069 | 11123.4552 | 10582.7317 | 10068.2933 | 9578.8624 | 9113.2233 | 8670.2193 | 8248.7503 | 7847.7694 | 7466.2806 | 7103.3364 | 6758.0354 | 6429.5198 | 6116.9737 | 5819.6208 | 5536.7225 | 5267.5763 | 5011.5136 | 4767.8983 | 4536.1255 | 4315.6194 | 4105.8323 | 3906.2433 | 3716.3564 | 0 | 0 | 15000 | 14270.8333 | 13577.1123 | 12917.1138 | 12289.1985 | 11691.8069 | 11123.4552 | 10582.7317 | 10068.2933 | 9578.8624 | 9113.2233 | 8670.2193 | 8248.7503 | 7847.7694 | 7466.2806 | 7103.3364 | 6758.0354 | 6429.5198 | 6116.9737 | 5819.6208 | 5536.7225 | 5267.5763 | 5011.5136 | 4767.8983 | 4536.1255 | 4315.6194 | 4105.8323 | 3906.2433 | 0 | 0 | 15000 | 14270.8333 | 13577.1123 | 12917.1138 | 12289.1985 | 11691.8069 | 11123.4552 | 10582.7317 | 10068.2933 | 9578.8624 | 9113.2233 | 8670.2193 | 8248.7503 | 7847.7694 | 7466.2806 | 7103.3364 | 6758.0354 | 6429.5198 | 6116.9737 | 5819.6208 | 5536.7225 | 5267.5763 | 5011.5136 | 4767.8983 | 4536.1255 | 4315.6194 | 4105.8323 | 3906.2433 | 3716.3564 | 0 | 0 | 15000 | 14270.8333 | 13577.1123 | 12917.1138 | 12289.1985 | 11691.8069 | 11123.4552 | 10582.7317 | 10068.2933 | 9578.8624
5 | [26 empty] | 15000 | 14270.8333 | 13577.1123 | 12917.1138 | 12289.1985 | 11691.8069 | 11123.4552 | 10582.7317 | 10068.2933 | 9578.8624 | 9113.2233 | 8670.2193 | 8248.7503 | 7847.7694 | 7466.2806 | 7103.3364 | 6758.0354 | 6429.5198 | 6116.9737 | 5819.6208 | 5536.7225 | 5267.5763 | 5011.5136 | 4767.8983 | 4536.1255 | 4315.6194 | 4105.8323 | 3906.2433 | 0 | 0 | 15000 | 14270.8333 | 13577.1123 | 12917.1138 | 12289.1985 | 11691.8069 | 11123.4552 | 10582.7317 | 10068.2933 | 9578.8624 | 9113.2233 | 8670.2193 | 8248.7503 | 7847.7694 | 7466.2806 | 7103.3364 | 6758.0354 | 6429.5198 | 6116.9737 | 5819.6208 | 5536.7225 | 5267.5763 | 5011.5136 | 4767.8983 | 4536.1255 | 4315.6194 | 4105.8323 | 3906.2433 | 0 | 0 | 15000 | 14270.8333 | 13577.1123 | 12917.1138 | 12289.1985 | 11691.8069 | 11123.4552 | 10582.7317 | 10068.2933 | 9578.8624 | 9113.2233 | 8670.2193 | 8248.7503 | 7847.7694 | 7466.2806 | 7103.3364 | 6758.0354 | 6429.5198 | 6116.9737 | 5819.6208 | 5536.7225 | 5267.5763 | 5011.5136 | 4767.8983 | 4536.1255 | 4315.6194 | 4105.8323 | 3906.2433 | 3716.3564 | 0 | 0 | 15000 | 14270.8333 | 13577.1123 | 12917.1138 | 12289.1985 | 11691.8069 | 11123.4552
[17 empty] | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
[17 empty] | 0 | 38.8294 | 101.6575 | 96.7158 | 130.8437 | 124.4832 | 118.432 | 177.3905 | 168.7673 | 160.5634 | 217.4738 | 183.3115 | 174.4005 | 165.9227 | 198.9819 | 189.3092 | 180.1066 | 236.0671 | 224.5916 | 213.674 | 203.287 | 193.405 | 184.0034 | 175.0588 | 166.549 | 158.4528 | 150.7503 | 143.4221 | 136.4502 | 129.8172 | 123.5067 | 117.5029 | 111.7909 | 106.3566 | 88.0504 | 83.7702 | 129.1593 | 122.8807 | 165.5892 | 157.5397 | 214.5972 | 187.3124 | 178.2069 | 191.116 | 181.8256 | 156.9531 | 149.3234 | 206.7803 | 196.7285 | 171.1684 | 162.8477 | 230.433 | 219.2314 | 208.5743 | 198.4353 | 188.7891 | 179.6119 | 170.8808 | 163.952 | 157.327 | 150.9918 | 144.933 | 139.138 | 132.3744 | 109.9057 | 104.5631 | 148.162 | 140.9597 | 182.7894 | 173.9038 | 230.1658 | 218.9771 | 208.3324 | 198.2051 | 188.5702 | 163.3698 | 155.4282 | 202.05 | 192.2281 | 247.5993 | 235.5633 | 224.1123 | 213.2179 | 202.8532 | 192.9922 | 183.6107 | 174.6852 | 166.1935 | 158.1147 | 150.4285 | 143.116 | 136.159 | 129.5402 | 123.2431 | 101.2183 | 96.298 | 156.3325 | 133.4786 | 126.9901 | 170.2783 | 162.0008 | 218.8414 | 208.2033 | 198.0823 | 188.4533 | 179.2924 | 170.5768 | 162.2849
Oil Price | 65
OP Cost FrPS $/BBL | 6 | [15 empty] | 0 | 9000 | 23562.5 | 22417.1007 | 30327.3805 | 28853.1329 | 27450.55 | 41116.1483 | 39117.4466 | 37215.9041 | 50406.7976 | 42488.5332 | 40423.1184 | 38458.1057 | 46120.6805 | 43878.703 | 41745.7105 | 54716.4051 | 52056.5799 | 49526.0517 | 47118.5353 | 44828.0509 | 42648.9096 | 40575.6987 | 38603.2689 | 36726.7211 | 34941.3944 | 33242.8544 | 31626.8823 | 30089.4644 | 28626.7821 | 27235.2024 | 25911.269 | 24651.6934 | 20408.611 | 19416.5258 | 29936.9667 | 28481.6975 | 38380.8141 | 36515.08 | 49740.0414 | 43415.8795 | 41305.3853 | 44297.4847 | 42144.1347 | 36379.1051 | 34610.6763 | 47928.2129 | 45598.3692 | 39673.9634 | 37745.368 | 53410.5237 | 50814.1788 | 48344.0451 | 45993.9874 | 43758.1685 | 41631.0354 | 39607.3045 | 38001.3367 | 36465.7716 | 34997.3707 | 33593.0485 | 32249.8655 | 30682.1637 | 25474.3132 | 24235.9786 | 34341.4843 | 32672.1066 | 42367.5227 | 40307.9904 | 53348.5742 | 50755.2407 | 48287.9721 | 45940.6401 | 43707.4145 | 37866.3921 | 36025.6647 | 46831.8134 | 44555.2669 | 57389.3859 | 54599.6241 | 51945.4757 | 49420.3484 | 47017.9704 | 44732.3746 | 42557.8841 | 40489.0981 | 38520.8781 | 36648.3354 | 34866.8191 | 33171.9043 | 31559.3811 | 30025.2445 | 28565.6841 | 23460.718 | 22320.2664 | 36235.2535 | 30938.1173 | 29434.181 | 39467.6526 | 37549.0861 | 50723.7833 | 48258.0439 | 45912.1667 | 43680.3253 | 41556.9761 | 39536.8454 | 37614.9154
Oil Price - OP Cost FrPS | 59
Rate per Well | 15000
Revenue ($ MM) | -2 | -5 | -5 | -81.5 | -206.5 | -125.5 | -176.5 | -176.5 | -125.5 | -176.5 | -176.5 | -96.5 | -20 | -20 | -10 | -40.5 | -45.5 | 33.8294 | 61.1575 | 56.2158 | 90.3437 | 83.9832 | 77.932 | 136.8905 | 128.2673 | 120.0634 | 176.9738 | 183.3115 | 133.9005 | 125.4227 | 198.9819 | 148.8092 | 139.6066 | 236.0671 | 224.5916 | 213.674 | 203.287 | 152.905 | 143.5034 | 175.0588 | 166.549 | 117.9528 | 110.2503 | 143.4221 | 136.4502 | 89.3172 | 83.0067 | 117.5029 | 111.7909 | 106.3566 | 47.5504 | 43.2702 | 88.6593 | 82.3807 | 125.0892 | 117.0397 | 214.5972 | 146.8124 | 137.7069 | 191.116 | 181.8256 | 116.4531 | 108.8234 | 206.7803 | 196.7285 | 130.6684 | 122.3477 | 230.433 | 219.2314 | 168.0743 | 157.9353 | 188.7891 | 179.6119 | 130.3808 | 123.452 | 157.327 | 110.4918 | 104.433 | 139.138 | 132.3744 | 69.4057 | 64.0631 | 107.662 | 100.4597 | 142.2894 | 133.4038 | 189.6658 | 178.4771 | 208.3324 | 198.2051 | 188.5702 | 122.8698 | 114.9282 | 161.55 | 151.7281 | 247.5993 | 235.5633 | 224.1123 | 172.7179 | 162.3532 | 192.9922 | 183.6107 | 134.1852 | 125.6935 | 158.1147 | 109.9285 | 102.616 | 136.159 | 129.5402 | 123.2431 | 60.7183 | 55.798 | 156.3325 | 92.9786 | 86.4901 | 129.7783 | 121.5008 | 218.8414 | 208.2033 | 198.0823 | 188.4533 | 179.2924 | 170.5768 | 162.2849
Cum Revenue ($MM) | -2 | -7 | -12 | -93.5 | -300 | -425.5 | -602 | -778.5 | -904 | -1080.5 | -1257 | -1353.5 | -1373.5 | -1393.5 | -1403.5 | -1444 | -1489.5 | -1455.6706 | -1394.5132 | -1338.2974 | -1247.9537 | -1163.9705 | -1086.0385 | -949.148 | -820.8807 | -700.8173 | -523.8435 | -340.532 | -206.6315 | -81.2088 | 117.7731 | 266.5823 | 406.1889 | 642.256 | 866.8476 | 1080.5216 | 1283.8086 | 1436.7136 | 1580.217 | 1755.2758 | 1921.8248 | 2039.7776 | 2150.0279 | 2293.45 | 2429.9003 | 2519.2175 | 2602.2242 | 2719.727 | 2831.518 | 2937.8746 | 2985.425 | 3028.6952 | 3117.3545 | 3199.7352 | 3324.8244 | 3441.8642 | 3656.4614 | 3803.2738 | 3940.9807 | 4132.0967 | 4313.9223 | 4430.3754 | 4539.1988 | 4745.9791 | 4942.7075 | 5073.3759 | 5195.7236 | 5426.1566 | 5645.388 | 5813.4624 | 5971.3977 | 6160.1868 | 6339.7987 | 6470.1795 | 6593.6315 | 6750.9585 | 6861.4503 | 6965.8833 | 7105.0213 | 7237.3957 | 7306.8014 | 7370.8645 | 7478.5266 | 7578.9863 | 7721.2757 | 7854.6794 | 8044.3452 | 8222.8223 | 8431.1548 | 8629.3599 | 8817.9301 | 8940.7999 | 9055.7281 | 9217.2781 | 9369.0063 | 9616.6056 | 9852.1688 | 10076.2811 | 10248.999 | 10411.3522 | 10604.3444 | 10787.9551 | 10922.1402 | 11047.8338 | 11205.9484 | 11315.8769 | 11418.493 | 11554.652 | 11684.1922 | 11807.4352 | 11868.1536 | 11923.9516 | 12080.284 | 12173.2627 | 12259.7528 | 12389.531 | 12511.0319 | 12729.8733 | 12938.0766 | 13136.1589 | 13324.6122 | 13503.9046 | 13674.4813 | 13836.7662
| 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050
Net Annual Revenue ($MM) | -93.5 | -685 | -575 | -90.5 | 105.7026 | 389.1494 | 608.616 | 607.1143 | 813.9393 | 674.7542 | 538.1742 | 426.277 | 308.9682 | 413.169 | 690.2325 | 613.8824 | 680.1775 | 734.0302 | 590.7717 | 486.4372 | 341.5906 | 643.8361 | 717.9776 | 675.8057 | 794.7466 | 636.4816 | 506.8182 | 369.2996 | 465.5795
Cum Net Revenue ($MM) | -93.5 | -778.5 | -1353.5 | -1444 | -1338.2974 | -949.148 | -340.532 | 266.5823 | 1080.5216 | 1755.2758 | 2293.45 | 2719.727 | 3028.6952 | 3441.8642 | 4132.0967 | 4745.9791 | 5426.1566 | 6160.1868 | 6750.9585 | 7237.3957 | 7578.9863 | 8222.8223 | 8940.7999 | 9616.6056 | 10411.3522 | 11047.8338 | 11554.652 | 11923.9516 | 12389.531 |  | 11250 | 2500 |  | 8750 | 546.875 | 0.048611 | 0.95139
IRR | 23.38% | [8 empty] | Oil Price | IRR
NPV at 7% Discount Rate ($M) | 3512.8317 | [8 empty] | 50 | 18
Facility Cost with Installation | 817 | M | [7 empty] | 60 | 22
Drilling and Completion Cost | 3148 | M | [7 empty] | 70 | 25
Total Development Cost | 3965 | M | [7 empty] | 80 | 29
| 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050
[5 empty] | 13744.9002 | 31936.8029 | 42307.1704 | 42220.1519 | 49511.1868 | 43792.7986 | 35878.5597 | 29394.5828 | 22597.0248 | 33328.6396 | 44689.6977 | 40265.5323 | 44107.0561 | 47227.595 | 38926.362 | 32880.6121 | 29180.9707 | 46694.832 | 43950.6047 | 46200.5327 | 50745.8546 | 41575.0587 | 34061.61 | 26092.9782 | 34018.8011