## Gantt Charts
Case | Year ---> | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 |  |  |  | 2032 |  |  |  | 2033 |  |  |  | 2034 |  |  |  | 2035 |  |  |  | 2036 |  |  |  | 2037 |  |  |  | 2038 |  |  |  | 2039 |  |  |  | 2040
SOP | Activity | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
20K Subsea | 1st and 2nd Appraisal | 90 | 90 | 90 | 90
7669.375 | 3rd Appraisal | [5 empty] | 76.5 | 76.5 | 76.5 | 76.5
| 1st Keeper Well (4th Appraisal Well) | [10 empty] | 76.5 | 76.5 | 76.5 | 76.5
| 2nd Keeper Well (5th Appraisal Well) | [15 empty] | 76.5 | 76.5
| FEED Eng'g & 20K Technology Qual | [5 empty] | 1 | 1 | 1 | 1 | 5 | 5 | 5 | 19 | 19 | 19 | 19 | 19 | 19
| FID | [17 empty] | 19 | 19.375
| Detailed Engineering, Procurement, Fabrication and Delivery | [18 empty] | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130
| Install, Commission Facility | [32 empty] | 180 | 180 | 180 | 180
| Complete 1st Keeper | [34 empty] | 140 | 140 | 140 | [11 empty] | 140 | 140 | [14 empty] | 0
| Complete 2nd Keeper | [37 empty] | 140 | 140 | [11 empty] | 140 | [14 empty] | 0 | 0
| Drill 3rd Well | [39 empty] | 140 | 140 | [10 empty] | 140 | 140 | [14 empty] | 0
| Complete 3rd Well | [41 empty] | 140 | [11 empty] | 140 | [14 empty] | 0 | 0
| Drill 4th Well | [42 empty] | 140 | 140 | [10 empty] | 140 | 140 | [14 empty] | 0
| Complete 4th Well | [44 empty] | 140 | [11 empty] | 140 | 140 | 140 | [12 empty] | 0 | 0
| Drill 5th Well | [45 empty] | 140 | 140 | [12 empty] | 140 | [13 empty] | 0
| Complete 5th Well | [47 empty] | 140 | [12 empty] | 140 | 140 | [12 empty] | 0 | 0
| Produce | [62 empty] | 140
3
Cum Total | [5 empty] | 3 | 77.5 | 77.5 | 77.5 | 77.5 | 5 | 81.5 | 81.5 | 95.5 | 95.5 | 19 | 95.5 | 95.5 | 38 | 149.375 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 310 | 180 | 320 | 320 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Millions | 0 | 0 | 0 | 0 | 3 | 80.5 | 158 | 235.5 | 313 | 318 | 399.5 | 481 | 576.5 | 672 | 691 | 786.5 | 882 | 920 | 1069.375 | 1199.375 | 1329.375 | 1459.375 | 1589.375 | 1719.375 | 1849.375 | 1979.375 | 2109.375 | 2239.375 | 2369.375 | 2499.375 | 2629.375 | 2759.375 | 3069.375 | 3249.375 | 3569.375 | 3889.375 | 4029.375 | 4169.375 | 4309.375 | 4449.375 | 4589.375 | 4729.375 | 4869.375 | 5009.375 | 5149.375 | 5289.375 | 5429.375 | 5569.375 | 5709.375 | 5849.375 | 5989.375 | 6129.375 | 6269.375 | 6409.375 | 6549.375 | 6689.375 | 6829.375 | 6969.375 | 7109.375 | 7249.375 | 7389.375 | 7529.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375 | 7669.375
[40 empty] | 15000 | 14550 | 14113.5 | 13690.095 | 13279.3921 | 12881.0104 | 12494.5801 | 12119.7427 | 11756.1504 | 11403.4659 | 11061.3619 | 10729.521 | 10407.6354 | 25095.4064 | 24342.5442 | 23612.2678 | 22903.8998 | 22216.7828 | 21550.2793 | 20903.7709 | 20276.6578 | 19668.3581 | 19078.3073 | 18505.9581 | 17950.7794 | 17412.256 | 16889.8883 | 16383.1917 | 15891.6959 | 15414.945 | 14952.4967 | 14503.9218 | 14068.8041 | 13646.74 | 13237.3378 | 12840.2177 | 12455.0111 | 12081.3608 | 11718.92 | 11367.3524 | 11026.3318 | 10695.5419 | 10374.6756 | 10063.4353 | 9761.5323 | 9468.6863 | 9184.6257 | 8909.0869 | 8641.8143 | 8382.5599 | 8131.0831 | 7887.1506 | 7650.5361 | 7421.02 | 7198.3894 | 6982.4377 | 6772.9646 | 6569.7757 | 6372.6824 | 6181.5019 | 5996.0569 | 5816.1752
[42 empty] | 15000 | 14550 | 14113.5 | 13690.095 | 13279.3921 | 12881.0104 | 12494.5801 | 12119.7427 | 11756.1504 | 11403.4659 | 11061.3619 | 10729.521 | 10407.6354 | 10095.4064 | 24792.5442 | 24048.7678 | 23327.3048 | 22627.4857 | 21948.6611 | 21290.2013 | 20651.4952 | 20031.9504 | 19430.9919 | 18848.0621 | 18282.6202 | 17734.1416 | 17202.1174 | 16686.0539 | 16185.4722 | 15699.9081 | 15228.9108 | 14772.0435 | 14328.8822 | 13899.0157 | 13482.0453 | 13077.5839 | 12685.2564 | 12304.6987 | 11935.5577 | 11577.491 | 11230.1663 | 10893.2613 | 10566.4634 | 10249.4695 | 9941.9855 | 9643.7259 | 9354.4141 | 9073.7817 | 8801.5682 | 8537.5212 | 8281.3956 | 8032.9537 | 7791.9651 | 7558.2061 | 7331.4599 | 7111.5161 | 6898.1707 | 6691.2255 | 6490.4888 | 6295.7741
[44 empty] | 15000 | 14550 | 14113.5 | 13690.095 | 13279.3921 | 12881.0104 | 12494.5801 | 12119.7427 | 11756.1504 | 11403.4659 | 11061.3619 | 10729.521 | 10407.6354 | 10095.4064 | 9792.5442 | 24498.7678 | 23763.8048 | 23050.8907 | 22359.3639 | 21688.583 | 21037.9255 | 20406.7878 | 19794.5841 | 19200.7466 | 18624.7242 | 18065.9825 | 17524.003 | 16998.2829 | 16488.3344 | 15993.6844 | 15513.8739 | 15048.4576 | 14597.0039 | 14159.0938 | 13734.321 | 13322.2914 | 12922.6226 | 12534.9439 | 12158.8956 | 11794.1288 | 11440.3049 | 11097.0957 | 10764.1829 | 10441.2574 | 10128.0197 | 9824.1791 | 9529.4537 | 9243.5701 | 8966.263 | 8697.2751 | 8436.3568 | 8183.2661 | 7937.7682 | 7699.6351 | 7468.6461 | 7244.5867 | 7027.2491 | 6816.4316
[47 empty] | 15000 | 14550 | 14113.5 | 13690.095 | 13279.3921 | 12881.0104 | 12494.5801 | 12119.7427 | 11756.1504 | 11403.4659 | 11061.3619 | 10729.521 | 10407.6354 | 10095.4064 | 9792.5442 | 24498.7678 | 23763.8048 | 23050.8907 | 22359.3639 | 21688.583 | 21037.9255 | 20406.7878 | 19794.5841 | 19200.7466 | 18624.7242 | 18065.9825 | 17524.003 | 16998.2829 | 16488.3344 | 15993.6844 | 15513.8739 | 15048.4576 | 14597.0039 | 14159.0938 | 13734.321 | 13322.2914 | 12922.6226 | 12534.9439 | 12158.8956 | 11794.1288 | 11440.3049 | 11097.0957 | 10764.1829 | 10441.2574 | 10128.0197 | 9824.1791 | 9529.4537 | 9243.5701 | 8966.263 | 8697.2751 | 8436.3568 | 8183.2661 | 7937.7682 | 7699.6351 | 7468.6461
[50 empty] | 15000 | 14550 | 14113.5 | 13690.095 | 13279.3921 | 12881.0104 | 12494.5801 | 12119.7427 | 11756.1504 | 11403.4659 | 11061.3619 | 10729.521 | 10407.6354 | 10095.4064 | 9792.5442 | 24498.7678 | 23763.8048 | 23050.8907 | 22359.3639 | 21688.583 | 21037.9255 | 20406.7878 | 19794.5841 | 19200.7466 | 18624.7242 | 18065.9825 | 17524.003 | 16998.2829 | 16488.3344 | 15993.6844 | 15513.8739 | 15048.4576 | 14597.0039 | 14159.0938 | 13734.321 | 13322.2914 | 12922.6226 | 12534.9439 | 12158.8956 | 11794.1288 | 11440.3049 | 11097.0957 | 10764.1829 | 10441.2574 | 10128.0197 | 9824.1791 | 9529.4537 | 9243.5701 | 8966.263 | 8697.2751 | 8436.3568 | 8183.2661
[40 empty] | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 |  |  |  |  | 102 | 102
[40 empty] | 41.6812 | 40.4308 | 80.8991 | 78.4722 | 117.7992 | 114.2653 | 110.8373 | 149.1934 | 144.7176 | 140.3761 | 177.8461 | 172.5107 | 167.3354 | 203.9966 | 197.8767 | 191.9404 | 227.8634 | 221.0275 | 214.3967 | 249.646 | 242.1566 | 234.8919 | 269.5264 | 261.4406 | 253.5974 | 287.6708 | 279.0406 | 270.6694 | 262.5493 | 254.6729 | 247.0327 | 239.6217 | 232.433 | 225.46 | 218.6962 | 212.1354 | 205.7713 | 199.5982 | 193.6102 | 187.8019 | 182.1678 | 176.7028 | 171.4017 | 166.2597 | 161.2719 | 156.4337 | 151.7407 | 147.1885 | 142.7728 | 138.4897 | 134.335 | 130.3049 | 126.3958 | 122.6039 | 118.9258 | 115.358 | 111.8973 | 108.5403 | 105.2841 | 102.1256 | 99.0618 | 96.09
Case | Year ---> | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 |  |  |  | 2032 |  |  |  | 2033 |  |  |  | 2034 |  |  |  | 2035 |  |  |  | 2036 |  |  |  | 2037 |  |  |  | 2038 |  |  |  | 2039 |  |  |  | 2040
FrPS | Activity | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
15K Dry Tree | 1st and 2nd Appraisal Wells | 90 | 90 | 90 | 90
3258 | 3rd Appraisal Well | [5 empty] | 76.5 | 76.5
| 1st Keeper Well (4th Appraisal Well) | [10 empty] | 76.5 | 76.5 | [16 empty] | 76.5 | 76.5
| 2nd Keeper Well (5th Appraisal Well) | [14 empty] | 76.5 | 76.5 | [16 empty] | 76.5 | 76.5
| Drill 3rd Well to 14" Casing | [16 empty] | 76.5 | [17 empty] | 76.5
| Drill 4th Well to 14" Casing | [17 empty] | 76.5 | [17 empty] | 76.5
| Drill 5th Well to 14" Casing | [18 empty] | 76.5 | [17 empty] | 76.5
| APS License | [5 empty] | 0 |  | 0 |  |  | 10
| Pre-FEED and FEED |  |  |  |  | 1 | 1 | 1 | 18 | 18 | 18
| FID (for APS deployment) | [9 empty] | 5 | 18
| Detailed Engineering, Procure, Fab and Delivery | [10 empty] | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | [9 empty] | 18 | 18
| Install, Commission Facility | [20 empty] | 25 | 25 | 25 | 25 | [6 empty] | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
| Complete 1st Keeper | [24 empty] | 40.5 | 5 | [14 empty] | 25 | 25 | 25 | 25 | [13 empty] | 0 | 0
| Complete 2nd Keeper | [26 empty] | 40.5 | [17 empty] | 40.5 | 5 | [12 empty] | 0 | 0
| Drill 3rd Well | [27 empty] | 40.5 | 5 | [17 empty] | 40.5 | [13 empty] | 0 | 0
| Complete 3rd Well | [28 empty] | 40.5 | 5 | [17 empty] | 40.5 | 5 | [12 empty] | 0 | 0
| Drill 4th Well | [30 empty] | 40.5 | [17 empty] | 40.5 | 5 | [13 empty] | 0 | 0
| Complete 4th Well | [31 empty] | 40.5 | 5 | [17 empty] | 40.5 | [13 empty] | 0 | 0
| Drill 5th Well | [32 empty] | 40.5 | 5 | [17 empty] | 40.5 | 5 | [13 empty] | 0 | 0
| Complete 5th Well | [33 empty] | 40.5 | 5 | [17 empty] | 40.5 | 5 | [13 empty] | 0 | 0
| Produce | [53 empty] | 40.5 | 5
Cum Total | Millions | 0 | 0 | 0 | 0 | 1 | 77.5 | 77.5 | 18 | 18 | 23 | 154.5 | 126.5 | 50 | 50 | 126.5 | 126.5 | 126.5 | 126.5 | 126.5 | 50 | 25 | 25 | 25 | 25 | 40.5 | 5 | 40.5 | 40.5 | 122 | 99.5 | 108.5 | 90.5 | 172 | 172 | 131.5 | 126.5 | 126.5 | 50 | 50 | 50 | 25 | 25 | 25 | 25 | 40.5 | 5 | 40.5 | 40.5 | 45.5 | 5 | 40.5 | 40.5 | 45.5 | 45.5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 1 | 78.5 | 156 | 174 | 192 | 215 | 369.5 | 496 | 546 | 596 | 722.5 | 849 | 975.5 | 1102 | 1228.5 | 1278.5 | 1303.5 | 1328.5 | 1353.5 | 1378.5 | 1419 | 1424 | 1464.5 | 1505 | 1627 | 1726.5 | 1835 | 1925.5 | 2097.5 | 2269.5 | 2401 | 2527.5 | 2654 | 2704 | 2754 | 2804 | 2829 | 2854 | 2879 | 2904 | 2944.5 | 2949.5 | 2990 | 3030.5 | 3076 | 3081 | 3121.5 | 3162 | 3207.5 | 3253 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258 | 3258
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 14640 | 14288.64 | 13945.7126 | 13611.0155 | 13284.3512 | 12965.5267 | 12654.3541 | 12350.6496 | 12054.234 | 11764.9324 | 11482.574 | 11206.9922 | 10938.0244 | 10675.5118 | 10419.2996 | 10169.2364 | 9925.1747 | 9686.9705 | 24454.4832 | 23867.5756 | 23294.7538 | 22735.6797 | 22190.0234 | 21657.4628 | 21137.6837 | 20630.3793 | 20135.2502 | 19652.0042 | 19180.3561 | 18720.0276 | 18270.7469 | 17832.249 | 17404.275 | 16986.5724 | 16578.8947 | 16181.0012 | 15792.6572 | 15413.6334 | 15043.7062 | 14682.6572 | 14330.2735 | 13986.3469 | 13650.6746 | 13323.0584 | 13003.305 | 12691.2257 | 12386.6362 | 12089.357 | 11799.2124 | 11516.0313 | 11239.6466 | 10969.895 | 10706.6176 | 10449.6587 | 10198.8669 | 9954.0941 | 9715.1959 | 9482.0312 | 9254.4624 | 9032.3553 | 8815.5788 | 8604.0049 | 8397.5088 | 8195.9686 | 7999.2653 | 7807.283 | 7619.9082 | 7437.0304 | 7258.5416 | 7084.3366 | 6914.3126 | 6748.3691 | 6586.4082
[30 empty] | 15000 | 14640 | 14288.64 | 13945.7126 | 13611.0155 | 13284.3512 | 12965.5267 | 12654.3541 | 12350.6496 | 12054.234 | 11764.9324 | 11482.574 | 11206.9922 | 10938.0244 | 10675.5118 | 10419.2996 | 10169.2364 | 9925.1747 | 9686.9705 | 24454.4832 | 23867.5756 | 23294.7538 | 22735.6797 | 22190.0234 | 21657.4628 | 21137.6837 | 20630.3793 | 20135.2502 | 19652.0042 | 19180.3561 | 18720.0276 | 18270.7469 | 17832.249 | 17404.275 | 16986.5724 | 16578.8947 | 16181.0012 | 15792.6572 | 15413.6334 | 15043.7062 | 14682.6572 | 14330.2735 | 13986.3469 | 13650.6746 | 13323.0584 | 13003.305 | 12691.2257 | 12386.6362 | 12089.357 | 11799.2124 | 11516.0313 | 11239.6466 | 10969.895 | 10706.6176 | 10449.6587 | 10198.8669 | 9954.0941 | 9715.1959 | 9482.0312 | 9254.4624 | 9032.3553 | 8815.5788 | 8604.0049 | 8397.5088 | 8195.9686 | 7999.2653 | 7807.283 | 7619.9082 | 7437.0304 | 7258.5416 | 7084.3366 | 6914.3126
[32 empty] | 15000 | 14640 | 14288.64 | 13945.7126 | 13611.0155 | 13284.3512 | 12965.5267 | 12654.3541 | 12350.6496 | 12054.234 | 11764.9324 | 11482.574 | 11206.9922 | 10938.0244 | 10675.5118 | 10419.2996 | 10169.2364 | 9925.1747 | 9686.9705 | 24454.4832 | 23867.5756 | 23294.7538 | 22735.6797 | 22190.0234 | 21657.4628 | 21137.6837 | 20630.3793 | 20135.2502 | 19652.0042 | 19180.3561 | 18720.0276 | 18270.7469 | 17832.249 | 17404.275 | 16986.5724 | 16578.8947 | 16181.0012 | 15792.6572 | 15413.6334 | 15043.7062 | 14682.6572 | 14330.2735 | 13986.3469 | 13650.6746 | 13323.0584 | 13003.305 | 12691.2257 | 12386.6362 | 12089.357 | 11799.2124 | 11516.0313 | 11239.6466 | 10969.895 | 10706.6176 | 10449.6587 | 10198.8669 | 9954.0941 | 9715.1959 | 9482.0312 | 9254.4624 | 9032.3553 | 8815.5788 | 8604.0049 | 8397.5088 | 8195.9686 | 7999.2653 | 7807.283 | 7619.9082 | 7437.0304 | 7258.5416
[34 empty] | 15000 | 14640 | 14288.64 | 13945.7126 | 13611.0155 | 13284.3512 | 12965.5267 | 12654.3541 | 12350.6496 | 12054.234 | 11764.9324 | 11482.574 | 11206.9922 | 10938.0244 | 10675.5118 | 10419.2996 | 10169.2364 | 9925.1747 | 9686.9705 | 9454.4832 | 24227.5756 | 23646.1138 | 23078.6071 | 22524.7205 | 21984.1272 | 21456.5081 | 20941.552 | 20438.9547 | 19948.4198 | 19469.6577 | 19002.3859 | 18546.3287 | 18101.2168 | 17666.7876 | 17242.7847 | 16828.9578 | 16425.0629 | 16030.8613 | 15646.1207 | 15270.6138 | 14904.119 | 14546.4202 | 14197.3061 | 13856.5708 | 13524.0131 | 13199.4367 | 12882.6503 | 12573.4667 | 12271.7035 | 11977.1826 | 11689.7302 | 11409.1767 | 11135.3564 | 10868.1079 | 10607.2733 | 10352.6987 | 10104.234 | 9861.7323 | 9625.0508 | 9394.0495 | 9168.5924 | 8948.5461 | 8733.781 | 8524.1703 | 8319.5902 | 8119.92 | 7925.042 | 7734.841
[36 empty] | 15000 | 14640 | 14288.64 | 13945.7126 | 13611.0155 | 13284.3512 | 12965.5267 | 12654.3541 | 12350.6496 | 12054.234 | 11764.9324 | 11482.574 | 11206.9922 | 10938.0244 | 10675.5118 | 10419.2996 | 10169.2364 | 9925.1747 | 9686.9705 | 9454.4832 | 9227.5756 | 24006.1138 | 23429.9671 | 22867.6479 | 22318.8243 | 21783.1725 | 21260.3764 | 20750.1273 | 20252.1243 | 19766.0733 | 19291.6875 | 18828.687 | 18376.7986 | 17935.7554 | 17505.2973 | 17085.1701 | 16675.126 | 16274.923 | 15884.3249 | 15503.1011 | 15131.0266 | 14767.882 | 14413.4528 | 14067.53 | 13729.9093 | 13400.3914 | 13078.782 | 12764.8913 | 12458.5339 | 12159.5291 | 11867.7004 | 11582.8756 | 11304.8865 | 11033.5693 | 10768.7636 | 10510.3133 | 10258.0658 | 10011.8722 | 9771.5872 | 9537.0692 | 9308.1795 | 9084.7832 | 8866.7484 | 8653.9464 | 8446.2517 | 8243.5417
[28 empty] | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44 | 44
[28 empty] | 48.2625 | 47.1042 | 94.2362 | 91.9745 | 138.0296 | 134.7169 | 179.7462 | 175.4323 | 219.4844 | 214.2168 | 209.0756 | 204.0578 | 199.1604 | 194.3806 | 189.7154 | 185.1623 | 180.7184 | 176.3811 | 172.148 | 216.2789 | 211.0882 | 254.2846 | 248.1818 | 290.4879 | 283.5162 | 276.7118 | 318.3332 | 310.6932 | 303.2366 | 344.2214 | 335.9601 | 327.8971 | 320.0275 | 312.3469 | 304.8505 | 297.5341 | 290.3933 | 283.4239 | 276.6217 | 269.9828 | 263.5032 | 257.1791 | 251.0068 | 244.9827 | 239.1031 | 233.3646 | 227.7638 | 222.2975 | 216.9624 | 211.7553 | 206.6732 | 201.713 | 196.8719 | 192.147 | 187.5354 | 183.0346 | 178.6418 | 174.3543 | 170.1698 | 166.0858 | 162.0997 | 158.2093 | 154.4123 | 150.7064 | 147.0894 | 143.5593 | 140.1139 | 136.7511 | 133.4691 | 130.2659 | 127.1395 | 124.0881 | 121.11 | 118.2034
| Months from Start |  |  |  | Months from Start | -1.25 | -1 | -0.75 | -0.5 | -0.25 | 0 | 0.25 | 0.5 | 0.75 | 1 | 1.25 | 1.5 | 1.75 | 2 | 2.25 | 2.5 | 2.75 | 3 | 3.25 | 3.5 | 3.75 | 4 | 4.25 | 4.5 | 4.75 | 5 | 5.25 | 5.5 | 5.75 | 6 | 6.25 | 6.5 | 6.75 | 7 | 7.25 | 7.5 | 7.75 | 8 | 8.25 | 8.5 | 8.75 | 9 | 9.25 | 9.5 | 9.75 | 10 | 10.25 | 10.5 | 10.75 | 11 | 11.25 | 11.5 | 11.75 | 12 | 12.25 | 12.5 | 12.75 | 13 | 13.25 | 13.5 | 13.75 | 14 | 14.25 | 14.5 | 14.75 | 15 | 15.25 | 15.5 | 15.75 | 16 | 16.25 | 16.5 | 16.75 | 17 | 17.25 | 17.5 | 17.75 | 18 | 18.25 | 18.5 | 18.75 | 19 | 19.25 | 19.5 | 19.75 | 20 | 20.25 | 20.5 | 20.75 | 21 | 21.25 | 21.5 | 21.75 | 22 | 22.25 | 22.5
| APS |  |  |  | APS | -1 | -78.5 | -156 | -174 | -192 | -215 | -369.5 | -496 | -546 | -596 | -722.5 | -849 | -975.5 | -1102 | -1228.5 | -1278.5 | -1303.5 | -1328.5 | -1353.5 | -1378.5 | -1419 | -1424 | -1416.2375 | -1409.6333 | -1437.3971 | -1444.9226 | -1415.3929 | -1371.176 | -1363.4298 | -1359.9975 | -1272.013 | -1184.2962 | -1101.7206 | -947.6628 | -798.5024 | -654.1218 | -489.4064 | -329.2442 | -173.5258 | -22.1447 | 109.5033 | 320.7822 | 491.3704 | 705.155 | 907.8368 | 1193.3247 | 1436.3409 | 1672.5528 | 1945.386 | 2210.5792 | 2508.8158 | 2853.0373 | 3188.9974 | 3516.8944 | 3836.922 | 4149.2688 | 4454.1194 | 4751.6535 | 5042.0468 | 5325.4707 | 5602.0924 | 5872.0752 | 6135.5784 | 6392.7575 | 6643.7643 | 6888.747 | 7127.8501 | 7361.2147 | 7588.9785 | 7811.276 | 8028.2384 | 8239.9937 | 8446.6668 | 8648.3798 | 8845.2517 | 9037.3987 | 9224.9341 | 9407.9687 | 9586.6104 | 9760.9648 | 9931.1346 | 10097.2204 | 10259.3201 | 10417.5294 | 10571.9417 | 10722.6481 | 10869.7376 | 11013.2969 | 11153.4107 | 11290.1619 | 11423.631 | 11553.8968 | 11681.0363 | 11805.1244 | 11926.2345 | 12044.4378
| Semi Subsea |  |  |  | Semi Subsea | -3 | -80.5 | -158 | -235.5 | -313 | -318 | -399.5 | -481 | -576.5 | -672 | -691 | -786.5 | -882 | -920 | -1069.375 | -1199.375 | -1329.375 | -1459.375 | -1589.375 | -1719.375 | -1849.375 | -1979.375 | -2109.375 | -2239.375 | -2369.375 | -2499.375 | -2629.375 | -2759.375 | -3069.375 | -3249.375 | -3569.375 | -3889.375 | -4029.375 | -4169.375 | -4267.6938 | -4367.2629 | -4426.3638 | -4487.8916 | -4510.0924 | -4535.8271 | -4564.9898 | -4555.7964 | -4551.0787 | -4550.7026 | -4512.8565 | -4480.3458 | -4453.0105 | -4389.0139 | -4331.1372 | -4279.1969 | -4191.3335 | -4110.3059 | -4035.9093 | -3926.2632 | -3824.1066 | -3729.2146 | -3599.6882 | -3478.2476 | -3364.6501 | -3076.9794 | -2797.9387 | -2527.2693 | -2264.72 | -2010.0472 | -1763.0145 | -1523.3928 | -1290.9598 | -1065.4997 | -846.8035 | -634.6681 | -428.8968 | -229.2987 | -35.6885 | 152.1134 | 334.2813 | 510.9841 | 682.3858 | 848.6455 | 1009.9174 | 1166.3511 | 1318.0918 | 1465.2803 | 1608.0532 | 1746.5428 | 1880.8778 | 2011.1827 | 2137.5785 | 2260.1824 | 2379.1081 | 2494.4661 | 2606.3634 | 2714.9038 | 2820.1879 | 2922.3135 | 3021.3754 | 3117.4653
| Oil Price |  |  |  |  | 50
| Oil Price - OP Cost APS ($6/bbl) |  |  |  |  | 44
| Oil Price - OP Cost SOP ($12/bbl) |  |  |  |  | 38
| Initial Well Rate (bpd) |  |  |  |  | 15000
| Redrill Well Rate (bpd) |  |  |  |  | 0
| Months from Start |  |  |  | Months from Start | 0.25 | 0.5 | 0.75 | 1 | 1.25 | 1.5 | 1.75 | 2 | 2.25 | 2.5 | 2.75 | 3 | 3.25 | 3.5 | 3.75 | 4 | 4.25 | 4.5 | 4.75 | 5 | 5.25 | 5.5 | 5.75 | 6 | 6.25 | 6.5 | 6.75 | 7 | 7.25 | 7.5 | 7.75 | 8 | 8.25 | 8.5 | 8.75 | 9 | 9.25 | 9.5 | 9.75 | 10 | 10.25 | 10.5 | 10.75 | 11 | 11.25 | 11.5 | 11.75 | 12 | 12.25 | 12.5 | 12.75 | 13 | 13.25 | 13.5 | 13.75 | 14 | 14.25 | 14.5 | 14.75 | 15 | 15.25 | 15.5 | 15.75 | 16 | 16.25 | 16.5 | 16.75 | 17 | 17.25 | 17.5 | 17.75 | 18 | 18.25 | 18.5 | 18.75 | 19 | 19.25 | 19.5 | 19.75 | 20 | 20.25 | 20.5 | 20.75 | 21 | 21.25 | 21.5 | 21.75 | 22 | 22.25 | 22.5 | 22.75 | 23 | 23.25 | 23.5 | 23.75 | 24
| APS | [27 empty] | 15000 | 14640 | 29288.64 | 28585.7126 | 42899.6555 | 41870.0638 | 55865.1823 | 54524.4179 | 68215.8319 | 66578.6519 | 64980.7643 | 63421.2259 | 61899.1165 | 60413.5377 | 58963.6128 | 57548.4861 | 56167.3224 | 54819.3067 | 53503.6433 | 67219.5559 | 65606.2865 | 79031.7357 | 77134.974 | 90283.7346 | 88116.925 | 86002.1188 | 98938.0679 | 96563.5543 | 94246.029 | 106984.1243 | 104416.5053 | 101910.5092 | 99464.657 | 97077.5052 | 94747.6451 | 92473.7016 | 90254.3328 | 88088.2288 | 85974.1113 | 83910.7326 | 81896.875 | 79931.35 | 78012.9976 | 76140.6857 | 74313.3092 | 72529.7898 | 70789.0749 | 69090.1371 | 67431.9738 | 65813.6064 | 64234.0799 | 62692.4619 | 61187.8428 | 59719.3346 | 58286.0706 | 56887.2049 | 55521.912 | 54189.3861 | 52888.8408 | 51619.5086 | 50380.6404 | 49171.5051 | 47991.3889 | 46839.5956 | 45715.4453 | 44618.2746 | 43547.436 | 42502.2976 | 41482.2424 | 40486.6686 | 39514.9886 | 38566.6288 | 37641.0297
| Semi Subsea | [38 empty] | 15000 | 14550 | 29113.5 | 28240.095 | 42392.8921 | 41121.1054 | 39887.4722 | 53690.8481 | 52080.1226 | 50517.7189 | 64002.1874 | 62082.1217 | 60219.6581 | 73413.0684 | 71210.6763 | 69074.356 | 82002.1253 | 79542.0616 | 77155.7997 | 89841.1257 | 87145.892 | 84531.5152 | 96995.5697 | 94085.7027 | 91263.1316 | 103525.2376 | 100419.4805 | 97406.8961 | 94484.6892 | 91650.1485 | 88900.6441 | 86233.6247 | 83646.616 | 81137.2175 | 78703.101 | 76342.008 | 74051.7477 | 71830.1953 | 69675.2894 | 67585.0308 | 65557.4798 | 63590.7554 | 61683.0328 | 59832.5418 | 58037.5655 | 56296.4386 | 54607.5454 | 52969.3191 | 51380.2395 | 49838.8323 | 48343.6673 | 46893.3573 | 45486.5566 | 44121.9599 | 42798.3011 | 41514.3521 | 40268.9215 | 39060.8539 | 37889.0282 | 36752.3574 | 35649.7867 | 34580.2931
[28 empty] | 67 | 67 | 72 | 72 | 72 | 72 | 77 | 77 | 77 | 77 | 82 | 82 | 82 | 82 | 87 | 87 | 87 | 87 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92
[6 empty] | 5088.0753 | NPV (M$)
[6 empty] | 21.67% | IRR
[7 empty] | Time (Years) | 0.25 | 0.5 | 0.75 | 1 | 1.25 | 1.5 | 1.75 | 2 | 2.25 | 2.5 | 2.75 | 3 | 3.25 | 3.5 | 3.75 | 4 | 4.25 | 4.5 | 4.75 | 5 | 5.25 | 5.5 | 5.75 | 6 | 6.25 | 6.5 | 6.75 | 7 | 7.25 | 7.5 | 7.75 | 8 | 8.25 | 8.5 | 8.75 | 9 | 9.25 | 9.5 | 9.75 | 10 | 10.25 | 10.5 | 10.75 | 11 | 11.25 | 11.5 | 11.75 | 12 | 12.25 | 12.5 | 12.75 | 13 | 13.25 | 13.5 | 13.75 | 14 | 14.25 | 14.5 | 14.75 | 15 | 15.25 | 15.5 | 15.75 | 16 | 16.25 | 16.5 | 16.75 | 17 | 17.25 | 17.5 | 17.75 | 18 | 18.25 | 18.5 | 18.75 | 19 | 19.25 | 19.5 | 19.75 | 20 | 20.25 | 20.5 | 20.75 | 21 | 21.25 | 21.5 | 21.75 | 22 | 22.25 | 22.5 | 22.75 | 23 | 23.25 | 23.5 | 23.75 | 24
[7 empty] | Dry Tree | 15000 | 14550 | 14113.5 | 13690.095 | 13279.3921 | 12881.0104 | 12494.5801 | 12119.7427 | 11756.1504 | 11403.4659 | 11061.3619 | 10729.521 | 10407.6354 | 10095.4064 | 9792.5442 | 9498.7678 | 9213.8048 | 8937.3907 | 8669.2689 | 8409.1909 | 8156.9151 | 7912.2077 | 7674.8415 | 7444.5962 | 7221.2583 | 7004.6206 | 6794.482 | 6590.6475 | 6392.9281 | 12000 | 11640 | 11290.8 | 10952.076 | 10623.5137 | 10304.8083 | 9995.6641 | 9695.7941 | 9404.9203 | 9122.7727 | 8849.0895 | 8583.6168 | 8326.1083 | 8076.3251 | 7834.0353 | 7599.0143 | 7371.0438 | 7149.9125 | 6935.4152 | 6727.3527 | 6525.5321 | 6329.7662 | 6139.8732 | 5955.677 | 5777.0067 | 5603.6965 | 5435.5856 | 10000 | 9700 | 9409 | 9126.73 | 8852.9281 | 8587.3403 | 8329.72 | 8079.8284 | 7837.4336 | 7602.3106 | 7374.2413 | 7153.014 | 6938.4236 | 6730.2709 | 6528.3628 | 6332.5119 | 6142.5365 | 5958.2604 | 5779.5126 | 5606.1272 | 5437.9434 | 5274.8051 | 5116.561 | 4963.0641 | 4814.1722 | 4669.7471 | 4529.6546 | 4393.765 | 4261.9521 | 4134.0935 | 4010.0707 | 3889.7686 | 3773.0755 | 3659.8832 | 3550.0867 | 3443.5841 | 3340.2766 | 3240.0683 | 3142.8663 | 3048.5803
[7 empty] | Subsea | 15000 | 14460 | 13939.44 | 13437.6202 | 12953.8658 | 12487.5267 | 12037.9757 | 11604.6086 | 11186.8427 | 10784.1163 | 10395.8881 | 10021.6362 | 9660.8573 | 9313.0664 | 8977.796 | 8654.5954 | 8343.0299 | 8042.6809 | 7753.1443 | 7474.0311 | 7204.966 | 6945.5872 | 6695.5461 | 6454.5064 | 6222.1442 | 5998.147 | 5782.2137 | 5574.054 | 5373.3881 | 5179.9461 | 4993.4681 | 4813.7032 | 4640.4099 | 4473.3551 | 4312.3144 | 4157.071 | 4007.4165 | 3863.1495 | 3724.0761 | 3590.0094 | 3460.769 | 3336.1813 | 3216.0788 | 3100.3 | 2988.6892 | 2881.0964 | 2777.3769 | 2677.3913 | 2581.0052 | 2488.0891 | 2398.5178 | 2312.1712 | 2228.933 | 2148.6915 | 2071.3386 | 1996.7704 | 1924.8866 | 1855.5907 | 1788.7895 | 1724.393 | 1662.3149 | 1602.4715 | 1544.7826 | 1489.1704 | 1435.5603 | 1383.8801 | 1334.0604 | 1286.0342 | 1239.737 | 1195.1065 | 1152.0826 | 1110.6077 | 1070.6258 | 1032.0833 | 994.9283 | 959.1108 | 924.5829 | 891.2979 | 859.2111 | 828.2795 | 798.4615 | 769.7169 | 742.0071 | 715.2948 | 689.5442 | 664.7206 | 640.7907 | 617.7222 | 595.4842 | 574.0468 | 553.3811 | 533.4594 | 514.2548 | 495.7417 | 477.895 | 460.6907
0.06
[71 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
[72 empty] | -496 | -849 | -1278.5 |  |  |  | -1378.5
[6 empty] | -1 | -77.5 | -77.5 | -18 | -18 | -23 | -154.5 | -126.5 | -50 | -50 | -126.5 | -126.5 | -126.5 | -126.5 | -126.5 | -50 | -25 | -25 | -25 | -25 | -40.5 | -5 | 7.7625 | 6.6042 | -27.7638 | -7.5255 | 29.5296 | 44.2169 | 7.7462 | 3.4323 | 87.9844 | 87.7168 | 82.5756 | 154.0578 | 149.1604 | 144.3806 | 164.7154 | 160.1623 | 155.7184 | 151.3811 | 131.648 | 211.2789 | 170.5882 | 213.7846 | 202.6818 | 285.4879 | 243.0162 | 236.2118 | 272.8332 | 265.1932 | 298.2366 | 344.2214 | 335.9601 | 327.8971 | 320.0275 | 312.3469 | 304.8505 | 297.5341 | 290.3933 | 283.4239 | 276.6217 | 269.9828 | 263.5032 | 257.1791 | 251.0068 | 244.9827 | 239.1031 | 233.3646 | 227.7638 | 222.2975 | 216.9624 | 211.7553 | 206.6732 | 201.713 | 196.8719 | 192.147 | 187.5354 | 183.0346 | 178.6418 | 174.3543 | 170.1698 | 166.0858 | 162.0997 | 158.2093 | 154.4123 | 150.7064 | 147.0894 | 143.5593 | 140.1139 | 136.7511 | 133.4691 | 130.2659 | 127.1395 | 124.0881 | 121.11 | 118.2034
[6 empty] | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
[6 empty] | -174 | -322 | -353 | -454.5 | -100 | -31.1333 | 38.4573 | 186.8798 | 530.1744 | 631.9772 | 727.2997 | 967.3977 | 1180.4845 | 1296.2316 | 1176.2019 | 1067.2868 | 968.4571 | 878.779 | 797.405 | 723.5661 | 656.5646 | 595.7674 | 540.6 | 490.541
| Ensco Revenue |  |  |  |  | 2023: 38.25; 2024: 38.25; 2025: 0; 2026: 0; 2027: 38.25; 2028: 38.25; 2029: 38.25; 2030: 76.5; 2031: 76.5; 2037: 45; 2038: 45; 2039: 45; 2040: 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
| Ensco Expense |  |  |  |  | -0.5 | -0.5 | -0.5 | -9 | -9 | -11.5 | -64 | -50 | -50 | -50 | -50 | -50 | -50 | -50 | -50 | -50 | -25 | -25 | -25 | -25 | [5 empty] | -18 | -18 | -50 | -50 | -50 | -50 | -50 | -50 | -50 | -50 | -50 | -25 | -25 | -25
| Ensco Net Revenue |  |  |  |  | -0.5 | -0.5 | -0.5 | -9 | -9 | -11.5 | -25.75 | -11.75 | -50 | -50 | -11.75 | -11.75 | -11.75 | 26.5 | 26.5 | -50 | -25 | -25 | -25 | -25 | 45 | 45 | 45 | 45 | 45 | 27 | 27 | -5 | -5 | -5 | -5 | -5 | -5 | -5 | -5 | -5 | 20 | 20 | 20 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
| Ensco Cum Net Revenue |  |  |  |  | -0.5 | -1 | -1.5 | -10.5 | -19.5 | -31 | -56.75 | -68.5 | -118.5 | -168.5 | -180.25 | -192 | -203.75 | -177.25 | -150.75 | -200.75 | -225.75 | -250.75 | -275.75 | -300.75 | -255.75 | -210.75 | -165.75 | -120.75 | -75.75 | -48.75 | -21.75 | -26.75 | -31.75 | -36.75 | -41.75 | -46.75 | -51.75 | -56.75 | -61.75 | -66.75 | -46.75 | -26.75 | -6.75 | 83.25 | 173.25 | 263.25 | 353.25 | 443.25 | 533.25 | 623.25 | 713.25 | 803.25 | 893.25 | 983.25 | 1073.25 | 1163.25 | 1253.25 | 1343.25 | 1433.25 | 1523.25 | 1613.25 | 1703.25 | 1793.25 | 1883.25 | 1973.25 | 2063.25 | 2153.25 | 2243.25 | 2333.25 | 2423.25 | 2513.25 | 2603.25 | 2693.25 | 2783.25 | 2873.25 | 2963.25 | 3053.25 | 3143.25 | 3233.25 | 3323.25 | 3413.25 | 3503.25 | 3593.25 | 3683.25 | 3773.25 | 3863.25 | 3953.25 | 4043.25 | 4133.25 | 4223.25 | 4313.25 | 4403.25 | 4493.25 | 4583.25 | 4673.25 | 4763.25 | 4853.25 | 4943.25 | 5033.25 | 5123.25
[6 empty] | 2020: -10.5; 2024: -68.5; 2028: -192; 2032: -8.75; 2036: -100; 2040: 180 |  |  |  | 94 |  |  |  | -20 |  |  |  | -20 |  |  |  | 150 |  |  |  | 360 |  |  |  | 360 |  |  |  | 360 |  |  |  | 360 |  |  |  | 360 |  |  |  | 360 |  |  |  | 360 |  |  |  | 360 |  |  |  | 360 |  |  |  | 360 |  |  |  | 360 |  |  |  | 360 |  |  |  | 360 |  |  |  | 360 |  |  | 933847286.5244 | 27.73%
Dril-Quip Revenue
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 |  | IRR | NPV
[6 empty] | -10.5 | -68.5 | -192 | -8.75 | -100 | 180 | 94 | -20 | -20 | 150 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 | 360 |  | 27.16% | 1123.5701
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
Note on C3: LuisMendoza: Do not include in the economics
Note on M5: Roy Shilling: 90 days x 1MM for 15K MODU
Note on N5: Roy Shilling: 90 days x 1MM for 15K MODU
Note on O5: Roy Shilling: 90 days x 1MM for 15K MODU
Note on P5: Roy Shilling: 90 days x 1MM for 15K MODU
Note on M37: Roy Shilling: 90 days x 1MM for 15K MODU
Note on N37: Roy Shilling: 90 days x 1MM for 15K MODU
Note on O37: Roy Shilling: 90 days x 1MM for 15K MODU
Note on AE37: Roy Shilling: 90 days x 1MM for 15K MODU
Note on AF37: Roy Shilling: 90 days x 1MM for 15K MODU
Note on AG37: Roy Shilling: 90 days x 1MM for 15K MODU

## Sheet3
.6*

## Sheet2
Year --->
Activity
1st and 2nd Appraisal
3rd Appraisal
1st Keeper Well (4th Appraisal Well)
2nd Keeper Well (5th Appraisal Well)
FEED Eng'g & 20K Technology Qual
FID
Detailed Engineering, Procurement, Fabrication and Delivery
Install, Commission Facility
Complete 1st Keeper
Complete 2nd Keeper
Drill 3rd Well
Complete 3rd Well
Drill 4th Well
Complete 4th Well
Drill 5th Well
Complete 5th Well
Produce
0
0
Millions
0
0
0
0
0
0
0
0
0
| 0 | 0
| Year ---> | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 |  |  |  | 2032 |  |  |  | 2033 |  |  |  | 2034 |  |  |  | 2035 |  |  |  | 2036 |  |  |  | 2037 |  |  |  | 2038 |  |  |  | 2039 |  |  |  | 2040 |  |  |  | 2041 |  |  |  | 2042
| Activity | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
| 1st and 2nd Appraisal Wells | 58.5 | 58.5 | 58.5 | 58.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3258 | 3rd Appraisal Well | 0 | 0 | 0 | 0 | 0 | 49.725 | 49.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1st Keeper Well (4th Appraisal Well) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.725 | 49.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2nd Keeper Well (5th Appraisal Well) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.725 | 49.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drill 3rd Well to 14" Casing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drill 4th Well to 14" Casing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drill 5th Well to 14" Casing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.725 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| APS License | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pre-FEED and FEED | 0 | 0 | 0 | 0 | 0.65 | 0.65 | 0.65 | 11.7 | 11.7 | 11.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FID (for APS deployment) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.25 | 11.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Detailed Engineering, Procure, Fab and Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 32.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Install, Commission Facility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.25 | 16.25 | 16.25 | 16.25 | 0 | 0 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Complete 1st Keeper | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.325 | 3.25 | 0 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Complete 2nd Keeper | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.325 | 0 | [19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drill 3rd Well | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.325 | 3.25 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Complete 3rd Well | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.325 | 3.25 | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drill 4th Well | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Complete 4th Well | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.325 | 3.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Drill 5th Well | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.325 | 3.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Complete 5th Well | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.325 | 3.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Produce | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Millions | 58.5 | 58.5 | 58.5 | 58.5 | 0.65 | 50.375 | 50.375 | 11.7 | 11.7 | 14.95 | 100.425 | 82.225 | 32.5 | 32.5 | 82.225 | 82.225 | 82.225 | 82.225 | 82.225 | 32.5 | 16.25 | 16.25 | 16.25 | 16.25 | 26.325 | 3.25 | 26.325 | 26.325 | 29.575 | 3.25 | 26.325 | 26.325 | 29.575 | 29.575 | 3.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 58.5 | 117 | 175.5 | 234 | 234.65 | 285.025 | 335.4 | 347.1 | 358.8 | 373.75 | 474.175 | 556.4 | 588.9 | 621.4 | 703.625 | 785.85 | 868.075 | 950.3 | 1032.525 | 1065.025 | 1081.275 | 1097.525 | 1113.775 | 1130.025 | 1156.35 | 1159.6 | 1185.925 | 1212.25 | 1241.825 | 1245.075 | 1271.4 | 1297.725 | 1327.3 | 1356.875 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125 | 1360.125
0
0
0
0
0
0
0
0
0
0
[7 empty] | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052 | 2053 | 2054 | 2055 | 2056 | 2057 | 2058 | 2059 | 2060 | 2061 | 2062 | 2063 | 2064 | 2065 | 2066 | 2067 | 2068 | 2069 | 2070 | 2071 | 2072 | 2073 | 2074 | 2075 | 2076 | 2077 | 2078 | 2079 | 2080 | 2081 | 2082 | 2083 | 2084 | 2085 | 2086 | 2087 | 2088 | 2089 | 2090 | 2091 | 2092
[7 empty] | 113.1 | 241.8 | 311.675 | 295.425 | 91.325 | 111.8 | 115.05 | 62.4 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0

## Cost Breakdown
Mad Dog 2 |  | 20K Subsea | [10 empty] | APS | 20K Subsea | MD2
[5 empty] | Project Category | Frontier APS - 5 Wells |  |  | 20K Subsea - 5 Wells |  | Mad Dog 2 - 20 Wells | Facilites | 1095180960 | 2662047200 | 5132606400
Hull and Topsides | 1300000000 | Hull and Topsides | 1100000000 |  | Hull and Topsides | 355000000 |  | 248500000 | 1100000000 |  | 1300000000 | Drilling and Completion | 1092760000 | 1868200000 | 3428400000
Installation | 250000000 | Installation | 250000000 |  | Installation | 110000000 |  | 77000000 | 250000000 |  | 250000000 | Export | 180000000 | 330000000 | 330000000
HUC | 150000000 | HUC | 150000000 |  | HUC | 25000000 |  | 17500000 | 150000000 |  | 150000000 | Installation and HUC | 135000000 | 400000000 | 400000000
Mooring System | 150000000 | Mooring System | 150000000 |  | Mooring System | 150000000 |  | 105000000 | 150000000 |  | 150000000
Subsea (24 wells) | 2160000000 | Subsea (5 wells) | 550000000 |  | Well Systems/Subsea | 180000000 |  | 180000000 | 550000000 |  | 2160000000
Drilling/Completion Tangibles | 960000000 | Drilling/Completion Tangibles | 200000000 |  | Drilling/Completion Tangibles | 150000000 |  | 105000000 | 200000000 |  | 960000000 |  | 2502940960 | 5260247200 | 9291006400
Well Construction | 2468400000 | Well Construction | 1668200000 |  | Well Construction | 942760000 |  | 942760000 | 1668200000 |  | 2468400000
Export Pipelines - 2 x 12" x 60 miles | 300000000 | Export Pipelines - 2 x 12" x 60 miles | 300000000 |  | Export Pipelines 2 x 60 miles | 150000000 |  | 105000000 | 300000000 |  | 300000000
Export Risers | 30000000 | Export Risers | 30000000 |  | Export Risers | 30000000 |  | 21000000 | 30000000 |  | 30000000
Engineering & Prj Mgt @ 4% | 310736000 | Engineering & Prj Mgt @ 4% | 175928000 |  | Engineering & Prj Mgt @ 4% | 83710400 | 16742080 | 58597280 | 175928000 | 11728533.3333 | 310736000
Contingency @15% | 1211870400 | Contingency @15% | 686119200 |  | Contingency @15% | 326470560 | 32647056 | 228529392 | 686119200 | 159074613.3333 | 1211870400
Total | 9291006400 | Total | 5260247200 |  | Total ---> | 2502940960 |  | 2088886672 | 5260247200 |  | 9291006400
[5 empty] | Well Cost Drilling | 140497714.2857 |  |  | 240197142.8571
[5 empty] | Well Cost Completion | 78054285.7143 |  |  | 133442857.1429
[5 empty] | Total | 218552000 |  |  | 373640000
[5 empty] | Drilling Cost Per Quarter | 70248857.1429 |  |  | 120098571.4286
|  |  |  | 1275180960 | Completion Cost Per Quarter | 78054285.7143 |  |  | 133442857.1429
[5 empty] | Hull and Topsides | 355000000 |  |  | 1100000000
[5 empty] | Mooring System | 150000000 | 505000000 |  | 150000000 | 83333333.3333
[5 empty] | Installation and Hook up | 135000000 | 33750000 |  | 400000000
[5 empty] | Well Systems and Subsea | 180000000 |  |  | 550000000
[5 empty] | Export System | 180000000 |  |  | 330000000 | 82500000
[5 empty] | Well Construction | 1092760000 |  |  | 1868200000
[5 empty] | Engineering Management and Contingency | 410180960 |  |  | 862047200
[5 empty] | Total | 2502940960 |  |  | 5260247200
[6 empty] | Frontier APS - 5 Wells | 20K Subsea - 5 Wells |  | Frontier | 20K Subsea
[5 empty] | Hull and Topsides | 355000000 | 1100000000 |  | 380000000 | 1100000000
[5 empty] | Installation | 110000000 | 250000000 |  | 150000000 | 150000000
[5 empty] | HUC | 25000000 | 150000000 |  | 185000000 | 400000000
[5 empty] | Mooring System | 150000000 | 150000000 |  | 195000000 | 550000000
[5 empty] | Well Systems/Subsea | 180000000 | 550000000 |  | 170000000 | 330000000
[5 empty] | Drilling/Completion Tangibles | 150000000 | 200000000 |  | 1128920000 | 1868200000
[5 empty] | Well Construction | 942760000 | 1668200000 |  | 432948320 | 862047200
[5 empty] | Export Pipelines 2 x 60 miles | 150000000 | 300000000 |  | 2641868320 | 5260247200
[5 empty] | Export Risers | 30000000 | 30000000
[5 empty] | Engineering & Prj Mgt @ 4% | 83710400 | 175928000
[5 empty] | Contingency @15% | 326470560 | 686119200
[5 empty] | Total ---> | 2502940960 | 5260247200

## Figures
Years | 0.25 | 0.5 | 0.75 | 1 | 1.25 | 1.5 | 1.75 | 2 | 2.25 | 2.5 | 2.75 | 3 | 3.25 | 3.5 | 3.75 | 4 | 4.25 | 4.5 | 4.75 | 5 | 5.25 | 5.5 | 5.75 | 6 | 6.25 | 6.5 | 6.75 | 7 | 7.25 | 7.5 | 7.75 | 8 | 8.25 | 8.5 | 8.75 | 9 | 9.25 | 9.5 | 9.75 | 10 | 10.25 | 10.5 | 10.75 | 11 | 11.25 | 11.5 | 11.75 | 12 | 12.25 | 12.5 | 12.75 | 13 | 13.25 | 13.5 | 13.75 | 14 | 14.25 | 14.5 | 14.75 | 15 | 15.25 | 15.5 | 15.75 | 16 | 16.25 | 16.5 | 16.75 | 17 | 17.25 | 17.5 | 17.75 | 18 | 18.25 | 18.5 | 18.75 | 19 | 19.25 | 19.5 | 19.75 | 20 | 20.25 | 20.5 | 20.75 | 21 | 21.25 | 21.5
APS - $30 per bbl | -1 | -78.5 | -156 | -174 | -192 | -228 | -452.5 | -649 | -769 | -889 | -1085.5 | -1282 | -1478.5 | -1675 | -1871.5 | -1991.5 | -2016.5 | -2041.5 | -2066.5 | -2091.5 | -2132 | -2137 | -2151.175 | -2165.9818 | -2160.0802 | -2132.9123 | -2196.1234 | -2243.1415 | -2270.5981 | -2300.4077 | -2265.6889 | -2228.8434 | -2194.8021 | -2163.4979 | -2134.8649 | -2108.8392 | -2030.358 | -1954.3605 | -1880.7868 | -1809.5789 | -1756.18 | -1643.2097 | -1568.5707 | -1470.37 | -1380.4981 | -1227.0501 | -1112.9049 | -1002.4712 | -874.3349 | -750.3659 | -589.9641 | -402.207 | -218.956 | -40.103 | 134.4574 | 304.8285 | 471.1106 | 633.4019 | 791.7983 | 946.3931 | 1097.2777 | 1244.541 | 1388.27 | 1528.5495 | 1665.4624 | 1799.0893 | 1929.5091 | 2056.7989 | 2181.0337 | 2302.2869 | 2420.63 | 2536.1329 | 2648.8637 | 2758.889 | 2866.2737 | 2971.0811 | 3073.3731 | 3173.2102 | 3270.6511 | 3365.7535 | 3458.5734 | 3549.1657 | 3637.5837 | 3723.8797 | 3808.1046 | 3890.3081 | 3970.5387 | 4048.8437 | 4125.2695 | 4199.861 | 4272.6624 | 4343.7165 | 4413.0653 | 4480.7497 | 4546.8097
20K -$50 per bbl | -3 | -80.5 | -158 | -235.5 | -313 | -318 | -399.5 | -481 | -576.5 | -672 | -691 | -786.5 | -882 | -920 | -1069.375 | -1199.375 | -1329.375 | -1459.375 | -1589.375 | -1719.375 | -1849.375 | -1979.375 | -2109.375 | -2239.375 | -2369.375 | -2499.375 | -2629.375 | -2759.375 | -3069.375 | -3249.375 | -3569.375 | -3889.375 | -4029.375 | -4169.375 | -4267.6938 | -4367.2629 | -4426.3638 | -4487.8916 | -4510.0924 | -4535.8271 | -4564.9898 | -4555.7964 | -4551.0787 | -4550.7026 | -4512.8565 | -4480.3458 | -4453.0105 | -4389.0139 | -4331.1372 | -4279.1969 | -4191.3335 | -4110.3059 | -4035.9093 | -3926.2632 | -3824.1066 | -3729.2146 | -3599.6882 | -3478.2476 | -3364.6501 | -3076.9794 | -2797.9387 | -2527.2693 | -2264.72 | -2010.0472 | -1763.0145 | -1523.3928 | -1290.9598 | -1065.4997 | -846.8035 | -634.6681 | -428.8968 | -229.2987 | -35.6885 | 152.1134 | 334.2813 | 510.9841 | 682.3858 | 848.6455 | 1009.9174 | 1166.3511 | 1318.0918 | 1465.2803 | 1608.0532 | 1746.5428 | 1880.8778 | 2011.1827 | 2137.5785 | 2260.1824 | 2379.1081 | 2494.4661 | 2606.3634 | 2714.9038 | 2820.1879 | 2922.3135 | 3021.3754 | 3117.4653
APS - $50 per bbl | -1 | -78.5 | -156 | -174 | -192 | -228 | -452.5 | -649 | -769 | -889 | -1085.5 | -1282 | -1478.5 | -1675 | -1871.5 | -1991.5 | -2016.5 | -2041.5 | -2066.5 | -2091.5 | -2132 | -2137 | -2129.2375 | -2122.6333 | -2073.8971 | -2004.9226 | -2005.3929 | -1991.176 | -1936.9298 | -1886.9975 | -1752.513 | -1618.2962 | -1489.2206 | -1365.1628 | -1246.0024 | -1131.6218 | -966.9064 | -806.7442 | -651.0258 | -499.6447 | -367.9967 | -156.7178 | 13.8704 | 227.655 | 430.3368 | 715.8247 | 958.8409 | 1195.0528 | 1467.886 | 1733.0792 | 2031.3158 | 2375.5373 | 2711.4974 | 3039.3944 | 3359.422 | 3671.7688 | 3976.6194 | 4274.1535 | 4564.5468 | 4847.9707 | 5124.5924 | 5394.5752 | 5658.0784 | 5915.2575 | 6166.2643 | 6411.247 | 6650.3501 | 6883.7147 | 7111.4785 | 7333.776 | 7550.7384 | 7762.4937 | 7969.1668 | 8170.8798 | 8367.7517 | 8559.8987 | 8747.4341 | 8930.4687 | 9109.1104 | 9283.4648 | 9453.6346 | 9619.7204 | 9781.8201 | 9940.0294 | 10094.4417 | 10245.1481 | 10392.2376 | 10535.7969 | 10675.9107 | 10812.6619 | 10946.131 | 11076.3968 | 11203.5363 | 11327.6244 | 8918.0287 | 9016.5315
APS - $75 per bbl | -1 | -78.5 | -156 | -174 | -192 | -228 | -452.5 | -649 | -769 | -889 | -1085.5 | -1282 | -1478.5 | -1675 | -1871.5 | -1991.5 | -2016.5 | -2041.5 | -2066.5 | -2091.5 | -2132 | -2137 | -2114.4297 | -2093.3731 | -2015.7235 | -1918.5295 | -1876.6498 | -1821.0993 | -1711.7037 | -1607.9455 | -1406.1193 | -1206.1769 | -1012.9531 | -826.2866 | -646.0202 | -472.0001 | -249.0766 | -32.1032 | 179.0629 | 384.5609 | 569.027 | 846.6643 | 1082.0182 | 1373.8219 | 1652.6504 | 2027.2653 | 2357.2694 | 2678.3815 | 3048.8851 | 3409.4047 | 3800.6798 | 4250.5146 | 4689.5534 | 5118.0552 | 5536.273 | 5944.4536 | 6342.8378 | 6731.6608 | 7111.1521 | 7481.5356 | 7843.0299 | 8195.8483 | 8540.199 | 8876.2854 | 9204.3057 | 9524.4534 | 9836.9177 | 10141.8828 | 10439.5287 | 10730.0312 | 11013.5615 | 11290.2872 | 11560.3714 | 11823.9736 | 12081.2494 | 12332.3505 | 12577.4252 | 12816.6182 | 13050.0704 | 13277.9199 | 13500.3009 | 13717.3448 | 13929.1797 | 14135.9305 | 14337.7193 | 14534.6651 | 14726.8843 | 14914.4902 | 15097.5936 | 15276.3024 | 15450.7223 | 15620.9561 | 15787.1043 | 15949.2649 | 16107.5337 | 16262.004

## SLB Business Model
Case | Year ---> | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 |  |  |  | 2032 |  |  |  | 2033 |  |  |  | 2034 |  |  |  | 2035 |  |  |  | 2036 |  |  |  | 2037 |  |  |  | 2038 |  |  |  | 2039 |  |  |  | 2040
FrPS | Activity | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
DQ | 1st and 2nd Appraisal
1306 | 3rd Appraisal
1st Keeper Well (4th Appraisal Well)
2nd Keeper Well (5th Appraisal Well)
| APS License | [5 empty] | 0 |  | 0 |  |  | 10 | [18 empty] | 10
| Pre-FEED and FEED |  |  |  |  | 1 | 1 | 1 | 18 | 18 | 18 | [19 empty] | 18 | 18
| FID (for APS deployment) | [9 empty] | 18 | 18 | [19 empty] | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
| Detailed Engineering, Procure, Fab and Delivery | [10 empty] | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | [20 empty] | 25 | 25 | 25 | 25
| Install, Commission Facility | [20 empty] | 25 | 25 | 25 | 25
| Lease Rate | [20 empty] | -85.5 | -85.5 | -85.5 | -85.5 | -85.5 | -85.5 | -85.5 | -85.5 | -85.5 | -85.5 | -85.5 | -85.5 | -85.5 | -85.5 | -85.5 | -85.5 | -85.5 | -85.5 | -85.5 | -85.5 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171
Complete 1st Keeper
Complete 2nd Keeper
Complete 3rd Well
Drill 4th Well
Complete 4th Well
Drill 5th Well
Complete 5th Well
Produce
3
Cum Total | [5 empty] | 4 | 1 | 1 | 18 | 18 | 36 | 148 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | -60.5 | -60.5 | -60.5 | -60.5 | -85.5 | -85.5 | -85.5 | -85.5 | -85.5 | -57.5 | 32.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | -146 | -146 | -146 | -146 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171 | -171
| Millions | 0 | 0 | 0 | 0 | 4 | 5 | 6 | 24 | 42 | 78 | 226 | 346 | 466 | 586 | 706 | 826 | 946 | 1066 | 1186 | 1306 | 1245.5 | 1185 | 1124.5 | 1064 | 978.5 | 893 | 807.5 | 722 | 636.5 | 579 | 611.5 | 626 | 640.5 | 655 | 669.5 | 684 | 698.5 | 713 | 727.5 | 742 | 596 | 450 | 304 | 158 | -13 | -184 | -355 | -526 | -697 | -868 | -1039 | -1210 | -1381 | -1552 | -1723 | -1894 | -2065 | -2236 | -2407 | -2578 | -2749 | -2920 | -3091 | -3262 | -3433 | -3604 | -3775 | -3946 | -4117 | -4288 | -4459 | -4630 | -4801 | -4972 | -5143 | -5314 | -5485 | -5656 | -5827 | -5998 | -6169 | -6340 | -6511 | -6682 | -6853 | -7024 | -7195 | -7366 | -7537 | -7708 | -7879 | -8050 | -8221 | -8392 | -8563 | -8734 | -8905 | -9076 | -9247 | -9418
[28 empty] | 750 | 727.5 | 705.675 | 684.5047 | 663.9696 | 644.0505 | 624.729 | 605.9871 | 587.8075 | 570.1733 | 553.0681 | 536.4761 | 520.3818 | 1254.7703 | 1217.1272 | 1180.6134 | 1145.195 | 1110.8391 | 1077.514 | 1045.1885 | 1013.8329 | 983.4179 | 953.9154 | 925.2979 | 897.539 | 870.6128 | 844.4944 | 819.1596 | 794.5848 | 770.7473 | 747.6248 | 725.1961 | 703.4402 | 682.337 | 661.8669 | 642.0109 | 622.7506 | 604.068 | 585.946 | 568.3676 | 551.3166 | 534.7771 | 518.7338 | 503.1718 | 488.0766 | 473.4343 | 459.2313 | 445.4543 | 432.0907 | 419.128 | 406.5542 | 394.3575 | 382.5268 | 371.051 | 359.9195 | 349.1219 | 338.6482 | 328.4888 | 318.6341 | 309.0751 | 299.8028 | 290.8088 | 282.0845 | 273.622 | 265.4133 | 257.4509 | 249.7274 | 242.2356 | 234.9685 | 227.9194 | 221.0818 | 214.4494 | 208.0159 | 201.7754
[30 empty] | 750 | 727.5 | 705.675 | 684.5047 | 663.9696 | 644.0505 | 624.729 | 605.9871 | 587.8075 | 570.1733 | 553.0681 | 536.4761 | 520.3818 | 504.7703 | 1239.6272 | 1202.4384 | 1166.3652 | 1131.3743 | 1097.4331 | 1064.5101 | 1032.5748 | 1001.5975 | 971.5496 | 942.4031 | 914.131 | 886.7071 | 860.1059 | 834.3027 | 809.2736 | 784.9954 | 761.4455 | 738.6022 | 716.4441 | 694.9508 | 674.1023 | 653.8792 | 634.2628 | 615.2349 | 596.7779 | 578.8746 | 561.5083 | 544.6631 | 528.3232 | 512.4735 | 497.0993 | 482.1863 | 467.7207 | 453.6891 | 440.0784 | 426.8761 | 414.0698 | 401.6477 | 389.5983 | 377.9103 | 366.573 | 355.5758 | 344.9085 | 334.5613 | 324.5244 | 314.7887 | 305.345 | 296.1847 | 287.2992 | 278.6802 | 270.3198 | 262.2102 | 254.3439 | 246.7136 | 239.3122 | 232.1328 | 225.1688 | 218.4137
[32 empty] | 750 | 727.5 | 705.675 | 684.5047 | 663.9696 | 644.0505 | 624.729 | 605.9871 | 587.8075 | 570.1733 | 553.0681 | 536.4761 | 520.3818 | 504.7703 | 489.6272 | 1224.9384 | 1188.1902 | 1152.5445 | 1117.9682 | 1084.4292 | 1051.8963 | 1020.3394 | 989.7292 | 960.0373 | 931.2362 | 903.2991 | 876.2002 | 849.9141 | 824.4167 | 799.6842 | 775.6937 | 752.4229 | 729.8502 | 707.9547 | 686.716 | 666.1146 | 646.1311 | 626.7472 | 607.9448 | 589.7064 | 572.0152 | 554.8548 | 538.2091 | 522.0629 | 506.401 | 491.209 | 476.4727 | 462.1785 | 448.3131 | 434.8638 | 421.8178 | 409.1633 | 396.8884 | 384.9818 | 373.4323 | 362.2293 | 351.3625 | 340.8216 | 330.5969 | 320.679 | 311.0587 | 301.7269 | 292.6751 | 283.8948 | 275.378 | 267.1167 | 259.1032 | 251.3301 | 243.7902 | 236.4764
| Lease Rate | 950000 | [32 empty] | 750 | 727.5 | 705.675 | 684.5047 | 663.9696 | 644.0505 | 624.729 | 605.9871 | 587.8075 | 570.1733 | 553.0681 | 536.4761 | 520.3818 | 504.7703 | 489.6272 | 1224.9384 | 1188.1902 | 1152.5445 | 1117.9682 | 1084.4292 | 1051.8963 | 1020.3394 | 989.7292 | 960.0373 | 931.2362 | 903.2991 | 876.2002 | 849.9141 | 824.4167 | 799.6842 | 775.6937 | 752.4229 | 729.8502 | 707.9547 | 686.716 | 666.1146 | 646.1311 | 626.7472 | 607.9448 | 589.7064 | 572.0152 | 554.8548 | 538.2091 | 522.0629 | 506.401 | 491.209 | 476.4727 | 462.1785 | 448.3131 | 434.8638 | 421.8178 | 409.1633 | 396.8884 | 384.9818 | 373.4323 | 362.2293 | 351.3625 | 340.8216 | 330.5969 | 320.679 | 311.0587 | 301.7269 | 292.6751 | 283.8948 | 275.378 | 267.1167 | 259.1032
| Drilling Contractor Services | 100000 | [35 empty] | 750 | 727.5 | 705.675 | 684.5047 | 663.9696 | 644.0505 | 624.729 | 605.9871 | 587.8075 | 570.1733 | 553.0681 | 536.4761 | 520.3818 | 504.7703 | 489.6272 | 1224.9384 | 1188.1902 | 1152.5445 | 1117.9682 | 1084.4292 | 1051.8963 | 1020.3394 | 989.7292 | 960.0373 | 931.2362 | 903.2991 | 876.2002 | 849.9141 | 824.4167 | 799.6842 | 775.6937 | 752.4229 | 729.8502 | 707.9547 | 686.716 | 666.1146 | 646.1311 | 626.7472 | 607.9448 | 589.7064 | 572.0152 | 554.8548 | 538.2091 | 522.0629 | 506.401 | 491.209 | 476.4727 | 462.1785 | 448.3131 | 434.8638 | 421.8178 | 409.1633 | 396.8884 | 384.9818 | 373.4323 | 362.2293 | 351.3625 | 340.8216 | 330.5969 | 320.679 | 311.0587 | 301.7269 | 292.6751 | 283.8948
[28 empty] | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88 | 88
[28 empty] | 4.8262 | 4.6815 | 9.3673 | 9.0863 | 13.6399 | 13.2307 | 12.8338 | 17.275 | 16.7568 | 16.2541 | 20.5927 | 19.9749 | 19.3757 | 23.6207 | 22.912 | 22.2247 | 26.3842 | 25.5927 | 24.8249 | 28.9064 | 28.0392 | 27.198 | 31.2083 | 30.2721 | 29.3639 | 33.3092 | 32.31 | 31.3407 | 30.4004 | 29.4884 | 28.6038 | 27.7457 | 26.9133 | 26.1059 | 25.3227 | 24.563 | 23.8261 | 23.1114 | 22.418 | 21.7455 | 21.0931 | 20.4603 | 19.8465 | 19.2511 | 18.6736 | 18.1134 | 17.57 | 17.0429 | 16.5316 | 16.0356 | 15.5546 | 15.0879 | 14.6353 | 14.1962 | 13.7704 | 13.3572 | 12.9565 | 12.5678 | 12.1908 | 11.8251 | 11.4703 | 11.1262 | 10.7924 | 10.4687 | 10.1546 | 9.85 | 9.5545 | 9.2678 | 8.9898 | 8.7201 | 8.4585 | 8.2047 | 7.9586 | 7.7198
Case | Year ---> | 2016 |  |  |  | 2017 |  |  |  | 2018 |  |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 |  |  |  | 2032 |  |  |  | 2033 |  |  |  | 2034 |  |  |  | 2035 |  |  |  | 2036 |  |  |  | 2037 |  |  |  | 2038 |  |  |  | 2039 |  |  |  | 2040
APS | Activity | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Operator | 1st and 2nd Appraisal Wells | 90 | 90 | 90 | 90
7716.5 | 3rd Appraisal Well | [5 empty] | 76.5 | 76.5
| 1st Keeper Well (4th Appraisal Well) | [10 empty] | 76.5 | 76.5
| 2nd Keeper Well (5th Appraisal Well) | [14 empty] | 76.5 | 76.5
| Drill 3rd Well to 14" Casing | [16 empty] | 76.5
| Drill 4th Well to 14" Casing | [17 empty] | 76.5
| Drill 5th Well to 14" Casing | [18 empty] | 76.5
APS License
Pre-FEED and FEED
FID (for APS deployment)
Detailed Engineering, Procure, Fab and Delivery
| Install, Commission Facility | [20 empty] | 50 | 50 | 50 | 50
[22 empty] | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 189 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171
| Complete 1st Keeper | [24 empty] | 9 | 9
| Complete 2nd Keeper | [26 empty] | 9 | [17 empty] | 9 | 9
| Drill 3rd Well | [27 empty] | 9 | 9 | [17 empty] | 9
| Complete 3rd Well | [28 empty] | 9 | 5 | [17 empty] | 9 | 9
| Drill 4th Well | [30 empty] | 9 | [17 empty] | 9 | 9
| Complete 4th Well | [31 empty] | 9 | 5 | [17 empty] | 9
| Drill 5th Well | [32 empty] | 9 | 9 | [17 empty] | 9 | 9
| Complete 5th Well | [33 empty] | 9 | 9 | [17 empty] | 9 | 5
| Produce | [53 empty] | 9 | 9
Cum Total | Millions | 0 | 0 | 0 | 0 | 0 | 76.5 | 76.5 | 0 | 0 | 0 | 76.5 | 76.5 | 0 | 0 | 76.5 | 76.5 | 76.5 | 76.5 | 76.5 | 0 | 144.5 | 144.5 | 144.5 | 144.5 | 103.5 | 103.5 | 103.5 | 103.5 | 112.5 | 99.5 | 103.5 | 103.5 | 108.5 | 112.5 | 103.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 198 | 198 | 198 | 198 | 207 | 198 | 198 | 198 | 207 | 203 | 198 | 189 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171 | 171
[6 empty] | 0 | 76.5 | 153 | 153 | 153 | 153 | 229.5 | 306 | 306 | 306 | 382.5 | 459 | 535.5 | 612 | 688.5 | 688.5 | 833 | 977.5 | 1122 | 1266.5 | 1370 | 1473.5 | 1577 | 1680.5 | 1793 | 1892.5 | 1996 | 2099.5 | 2208 | 2320.5 | 2424 | 2518.5 | 2613 | 2707.5 | 2802 | 2896.5 | 2991 | 3085.5 | 3180 | 3274.5 | 3472.5 | 3670.5 | 3868.5 | 4066.5 | 4273.5 | 4471.5 | 4669.5 | 4867.5 | 5074.5 | 5277.5 | 5475.5 | 5664.5 | 5835.5 | 6006.5 | 6177.5 | 6348.5 | 6519.5 | 6690.5 | 6861.5 | 7032.5 | 7203.5 | 7374.5 | 7545.5 | 7716.5 | 7887.5 | 8058.5 | 8229.5 | 8400.5 | 8571.5 | 8742.5 | 8913.5 | 9084.5 | 9255.5 | 9426.5 | 9597.5 | 9768.5 | 9939.5 | 10110.5 | 10281.5 | 10452.5 | 10623.5 | 10794.5 | 10965.5 | 11136.5 | 11307.5 | 11478.5 | 11649.5 | 11820.5 | 11991.5 | 12162.5 | 12333.5 | 12504.5 | 12675.5 | 12846.5 | 13017.5 | 13188.5
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14250 | 13908 | 13574.208 | 13248.427 | 12930.4648 | 12620.1336 | 12317.2504 | 12021.6364 | 11733.1171 | 11451.5223 | 11176.6858 | 10908.4453 | 10646.6426 | 10391.1232 | 10141.7362 | 9898.3346 | 9660.7745 | 9428.916 | 9202.622 | 23231.759 | 22674.1968 | 22130.0161 | 21598.8957 | 21080.5222 | 20574.5897 | 20080.7995 | 19598.8603 | 19128.4877 | 18669.404 | 18221.3383 | 17784.0262 | 17357.2095 | 16940.6365 | 16534.0612 | 16137.2438 | 15749.9499 | 15371.9511 | 15003.0243 | 14642.9517 | 14291.5209 | 13948.5244 | 13613.7598 | 13287.0296 | 12968.1408 | 12656.9055 | 12353.1397 | 12056.6644 | 11767.3044 | 11484.8891 | 11209.2518 | 10940.2297 | 10677.6642 | 10421.4003 | 10171.2867 | 9927.1758 | 9688.9236 | 9456.3894 | 9229.4361 | 9007.9296 | 8791.7393 | 8580.7376 | 8374.7999 | 8173.8047 | 7977.6333 | 7786.1701 | 7599.3021 | 7416.9188 | 7238.9128 | 7065.1789 | 6895.6146 | 6730.1198 | 6568.5969 | 6410.9506 | 6257.0878
[30 empty] | 14250 | 13908 | 13574.208 | 13248.427 | 12930.4648 | 12620.1336 | 12317.2504 | 12021.6364 | 11733.1171 | 11451.5223 | 11176.6858 | 10908.4453 | 10646.6426 | 10391.1232 | 10141.7362 | 9898.3346 | 9660.7745 | 9428.916 | 9202.622 | 23231.759 | 22674.1968 | 22130.0161 | 21598.8957 | 21080.5222 | 20574.5897 | 20080.7995 | 19598.8603 | 19128.4877 | 18669.404 | 18221.3383 | 17784.0262 | 17357.2095 | 16940.6365 | 16534.0612 | 16137.2438 | 15749.9499 | 15371.9511 | 15003.0243 | 14642.9517 | 14291.5209 | 13948.5244 | 13613.7598 | 13287.0296 | 12968.1408 | 12656.9055 | 12353.1397 | 12056.6644 | 11767.3044 | 11484.8891 | 11209.2518 | 10940.2297 | 10677.6642 | 10421.4003 | 10171.2867 | 9927.1758 | 9688.9236 | 9456.3894 | 9229.4361 | 9007.9296 | 8791.7393 | 8580.7376 | 8374.7999 | 8173.8047 | 7977.6333 | 7786.1701 | 7599.3021 | 7416.9188 | 7238.9128 | 7065.1789 | 6895.6146 | 6730.1198 | 6568.5969
[32 empty] | 14250 | 13908 | 13574.208 | 13248.427 | 12930.4648 | 12620.1336 | 12317.2504 | 12021.6364 | 11733.1171 | 11451.5223 | 11176.6858 | 10908.4453 | 10646.6426 | 10391.1232 | 10141.7362 | 9898.3346 | 9660.7745 | 9428.916 | 9202.622 | 23231.759 | 22674.1968 | 22130.0161 | 21598.8957 | 21080.5222 | 20574.5897 | 20080.7995 | 19598.8603 | 19128.4877 | 18669.404 | 18221.3383 | 17784.0262 | 17357.2095 | 16940.6365 | 16534.0612 | 16137.2438 | 15749.9499 | 15371.9511 | 15003.0243 | 14642.9517 | 14291.5209 | 13948.5244 | 13613.7598 | 13287.0296 | 12968.1408 | 12656.9055 | 12353.1397 | 12056.6644 | 11767.3044 | 11484.8891 | 11209.2518 | 10940.2297 | 10677.6642 | 10421.4003 | 10171.2867 | 9927.1758 | 9688.9236 | 9456.3894 | 9229.4361 | 9007.9296 | 8791.7393 | 8580.7376 | 8374.7999 | 8173.8047 | 7977.6333 | 7786.1701 | 7599.3021 | 7416.9188 | 7238.9128 | 7065.1789 | 6895.6146
[34 empty] | 14250 | 13908 | 13574.208 | 13248.427 | 12930.4648 | 12620.1336 | 12317.2504 | 12021.6364 | 11733.1171 | 11451.5223 | 11176.6858 | 10908.4453 | 10646.6426 | 10391.1232 | 10141.7362 | 9898.3346 | 9660.7745 | 9428.916 | 9202.622 | 8981.759 | 23016.1968 | 22463.8081 | 21924.6767 | 21398.4845 | 20884.9208 | 20383.6827 | 19894.4744 | 19417.007 | 18950.9988 | 18496.1748 | 18052.2666 | 17619.0122 | 17196.1559 | 16783.4482 | 16380.6454 | 15987.51 | 15603.8097 | 15229.3183 | 14863.8146 | 14507.0831 | 14158.9131 | 13819.0992 | 13487.4408 | 13163.7422 | 12847.8124 | 12539.4649 | 12238.5178 | 11944.7933 | 11658.1183 | 11378.3234 | 11105.2437 | 10838.7178 | 10578.5886 | 10324.7025 | 10076.9096 | 9835.0638 | 9599.0223 | 9368.6457 | 9143.7982 | 8924.3471 | 8710.1627 | 8501.1188 | 8297.092 | 8097.9618 | 7903.6107 | 7713.924 | 7528.7899 | 7348.0989
[36 empty] | 14250 | 13908 | 13574.208 | 13248.427 | 12930.4648 | 12620.1336 | 12317.2504 | 12021.6364 | 11733.1171 | 11451.5223 | 11176.6858 | 10908.4453 | 10646.6426 | 10391.1232 | 10141.7362 | 9898.3346 | 9660.7745 | 9428.916 | 9202.622 | 8981.759 | 8766.1968 | 22805.8081 | 22258.4687 | 21724.2655 | 21202.8831 | 20694.0139 | 20197.3576 | 19712.621 | 19239.5181 | 18777.7696 | 18327.1032 | 17887.2527 | 17457.9586 | 17038.9676 | 16630.0324 | 16230.9116 | 15841.3697 | 15461.1769 | 15090.1086 | 14727.946 | 14374.4753 | 14029.4879 | 13692.7802 | 13364.1535 | 13043.4138 | 12730.3719 | 12424.8429 | 12126.6467 | 11835.6072 | 11551.5526 | 11274.3153 | 11003.7318 | 10739.6422 | 10481.8908 | 10230.3254 | 9984.7976 | 9745.1625 | 9511.2786 | 9283.0079 | 9060.2157 | 8842.7705 | 8630.544 | 8423.411 | 8221.2491 | 8023.9391 | 7831.3646
[28 empty] | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94 | 94
[28 empty] | 97.9509 | 95.6001 | 191.2566 | 186.6665 | 280.1374 | 273.4141 | 364.8031 | 356.0479 | 445.4536 | 434.7628 | 424.3285 | 414.1446 | 404.2051 | 394.5042 | 385.0361 | 375.7952 | 366.7761 | 357.9735 | 349.3821 | 438.9479 | 428.4132 | 516.0822 | 503.6962 | 589.5584 | 575.409 | 561.5992 | 646.0718 | 630.566 | 615.4325 | 698.613 | 681.8463 | 665.482 | 649.5104 | 633.9222 | 618.708 | 603.8591 | 589.3664 | 575.2216 | 561.4163 | 547.9423 | 534.7917 | 521.9567 | 509.4298 | 497.2034 | 485.2706 | 473.6241 | 462.2571 | 451.1629 | 440.335 | 429.767 | 419.4526 | 409.3857 | 399.5604 | 389.971 | 380.6117 | 371.477 | 362.5616 | 353.8601 | 345.3674 | 337.0786 | 328.9887 | 321.093 | 313.3868 | 305.8655 | 298.5247 | 291.3601 | 284.3675 | 277.5427 | 270.8816 | 264.3805 | 258.0353 | 251.8425 | 245.7983 | 239.8991
| Months from Start |  |  |  | Months from Start | 0 | 0.25 | 0.5 | 0.75 | 1 | 1.25 | 1.5 | 1.75 | 2 | 2.25 | 2.5 | 2.75 | 3 | 3.25 | 3.5 | 3.75 | 4 | 4.25 | 4.5 | 4.75 | 5 | 5.25 | 5.5 | 5.75 | 6 | 6.25 | 6.5 | 6.75 | 7 | 7.25 | 7.5 | 7.75 | 8 | 8.25 | 8.5 | 8.75 | 9 | 9.25 | 9.5 | 9.75 | 10 | 10.25 | 10.5 | 10.75 | 11 | 11.25 | 11.5 | 11.75 | 12 | 12.25 | 12.5 | 12.75 | 13 | 13.25 | 13.5 | 13.75 | 14 | 14.25 | 14.5 | 14.75 | 15 | 15.25 | 15.5 | 15.75 | 16 | 16.25 | 16.5 | 16.75 | 17 | 17.25 | 17.5 | 17.75 | 18 | 18.25 | 18.5 | 18.75 | 19 | 19.25 | 19.5 | 19.75 | 20 | 20.25 | 20.5 | 20.75 | 21 | 21.25 | 21.5 | 21.75 | 22 | 22.25 | 22.5 | 22.75 | 23 | 23.25 | 23.5 | 23.75
| APS |  |  |  | Operator | 0 | -76.5 | -153 | -153 | -153 | -153 | -229.5 | -306 | -306 | -306 | -382.5 | -459 | -535.5 | -612 | -688.5 | -688.5 | -833 | -977.5 | -1122 | -1266.5 | -1370 | -1473.5 | -1479.0491 | -1486.9489 | -1408.1923 | -1321.0258 | -1144.3884 | -974.4742 | -718.1711 | -474.6233 | -132.6696 | 207.5931 | 537.4216 | 857.0662 | 1166.7713 | 1466.7754 | 1757.3115 | 2038.6067 | 2310.8829 | 2574.3564 | 2725.7385 | 2966.6864 | 3197.0995 | 3515.1817 | 3811.8779 | 4203.4364 | 4580.8454 | 4944.4446 | 5383.5164 | 5811.0824 | 6228.5149 | 6738.1279 | 7248.9742 | 7743.4562 | 8221.9666 | 8684.8888 | 9132.5968 | 9565.4559 | 9983.8223 | 10388.044 | 10778.4603 | 11155.4026 | 11519.1943 | 11870.151 | 12208.5808 | 12534.7842 | 12849.0548 | 13151.6788 | 13442.9359 | 13723.0988 | 13992.4338 | 14251.2008 | 14499.6533 | 14738.039 | 14966.5995 | 15185.5705 | 15395.1821 | 15595.6592 | 15787.2207 | 15970.0808 | 16144.4482 | 16310.5268 | 16468.5156 | 16618.6086 | 16760.9953 | 16895.8608 | 17023.3855 | 17143.7457 | 17257.1131 | 17363.6558 | 17463.5374 | 17556.9179 | 17643.9533 | 17724.7958 | 17799.594 | 17868.4932
| Semi Subsea |  |  |  | SLB | -4 | -5 | -6 | -24 | -42 | -78 | -226 | -346 | -466 | -586 | -706 | -826 | -946 | -1066 | -1186 | -1306 | -1245.5 | -1185 | -1124.5 | -1064 | -978.5 | -893 | -802.6738 | -712.4923 | -617.625 | -551.0388 | -569.8989 | -571.1681 | -572.8343 | -570.0593 | -567.8025 | -566.0485 | -559.9558 | -554.4808 | -549.6052 | -540.4845 | -371.5725 | -203.3478 | -30.9636 | 140.629 | 336.4539 | 536.3603 | 735.3995 | 933.5975 | 1135.8058 | 1337.0779 | 1537.4418 | 1741.7511 | 1945.061 | 2147.4017 | 2348.8022 | 2549.2906 | 2748.8944 | 2947.64 | 3145.5533 | 3342.6592 | 3538.982 | 3734.545 | 3929.3712 | 4123.4825 | 4316.9005 | 4509.646 | 4701.7391 | 4893.1995 | 5084.046 | 5274.2971 | 5463.9707 | 5653.0841 | 5841.6541 | 6029.6969 | 6217.2285 | 6404.2642 | 6590.8187 | 6776.9067 | 6962.542 | 7147.7382 | 7332.5086 | 7516.8658 | 7700.8223 | 7884.3902 | 8067.581 | 8250.406 | 8432.8764 | 8615.0026 | 8796.795 | 8978.2636 | 9159.4182 | 9340.2682 | 9520.8226 | 9701.0905 | 9881.0802 | 10060.8003 | 10240.2588 | 10419.4636 | 10598.4222 | 10777.142
| Oil Price |  |  |  |  | 100
| Oil Price - OP Cost APS ($6/bbl) |  |  |  |  | 94
| Oil Price - OP Cost SOP ($12/bbl) |  |  |  |  | 88
| Initial Well Rate (bpd) |  |  |  |  | 15000
| Redrill Well Rate (bpd) |  |  |  |  | 0
| Months from Start |  |  |  | Months from Start | 0.25 | 0.5 | 0.75 | 1 | 1.25 | 1.5 | 1.75 | 2 | 2.25 | 2.5 | 2.75 | 3 | 3.25 | 3.5 | 3.75 | 4 | 4.25 | 4.5 | 4.75 | 5 | 5.25 | 5.5 | 5.75 | 6 | 6.25 | 6.5 | 6.75 | 7 | 7.25 | 7.5 | 7.75 | 8 | 8.25 | 8.5 | 8.75 | 9 | 9.25 | 9.5 | 9.75 | 10 | 10.25 | 10.5 | 10.75 | 11 | 11.25 | 11.5 | 11.75 | 12 | 12.25 | 12.5 | 12.75 | 13 | 13.25 | 13.5 | 13.75 | 14 | 14.25 | 14.5 | 14.75 | 15 | 15.25 | 15.5 | 15.75 | 16 | 16.25 | 16.5 | 16.75 | 17 | 17.25 | 17.5 | 17.75 | 18 | 18.25 | 18.5 | 18.75 | 19 | 19.25 | 19.5 | 19.75 | 20 | 20.25 | 20.5 | 20.75 | 21 | 21.25 | 21.5 | 21.75 | 22 | 22.25 | 22.5 | 22.75 | 23 | 23.25 | 23.5 | 23.75 | 24
| APS | [27 empty] | 14250 | 13908 | 27824.208 | 27156.427 | 40754.6728 | 39776.5606 | 53071.9232 | 51798.197 | 64805.0403 | 63249.7193 | 61731.726 | 60250.1646 | 58804.1607 | 57392.8608 | 56015.4322 | 54671.0618 | 53358.9563 | 52078.3413 | 50828.4612 | 63858.5781 | 62325.9722 | 75080.1489 | 73278.2253 | 85769.5479 | 83711.0788 | 81702.0129 | 93991.1646 | 91735.3766 | 89533.7276 | 101634.9181 | 99195.6801 | 96814.9837 | 94491.4241 | 92223.63 | 90010.2628 | 87850.0165 | 85741.6161 | 83683.8173 | 81675.4057 | 79715.196 | 77802.0313 | 75934.7825 | 74112.3478 | 72333.6514 | 70597.6438 | 68903.3003 | 67249.6211 | 65635.6302 | 64060.3751 | 62522.9261 | 61022.3759 | 59557.8388 | 58128.4507 | 56733.3679 | 55371.7671 | 54042.8446 | 52745.8164 | 51479.9168 | 50244.3988 | 49038.5332 | 47861.6084 | 46712.9298 | 45591.8195 | 44497.6158 | 43429.673 | 42387.3609 | 41370.0642 | 40377.1827 | 39408.1303 | 38462.3352 | 37539.2391 | 36638.2974 | 35758.9783
| Semi Subsea | [38 empty] | 750 | 727.5 | 1455.675 | 1412.0048 | 2119.6446 | 2056.0553 | 1994.3736 | 2684.5424 | 2604.0061 | 2525.8859 | 3200.1094 | 3104.1061 | 3010.9829 | 3670.6534 | 3560.5338 | 3453.7178 | 4100.1063 | 3977.1031 | 3857.79 | 4492.0563 | 4357.2946 | 4226.5758 | 4849.7785 | 4704.2851 | 4563.1566 | 5176.2619 | 5020.974 | 4870.3448 | 4724.2345 | 4582.5074 | 4445.0322 | 4311.6812 | 4182.3308 | 4056.8609 | 3935.155 | 3817.1004 | 3702.5874 | 3591.5098 | 3483.7645 | 3379.2515 | 3277.874 | 3179.5378 | 3084.1516 | 2991.6271 | 2901.8783 | 2814.8219 | 2730.3773 | 2648.466 | 2569.012 | 2491.9416 | 2417.1834 | 2344.6679 | 2274.3278 | 2206.098 | 2139.9151 | 2075.7176 | 2013.4461 | 1953.0427 | 1894.4514 | 1837.6179 | 1782.4893 | 1729.0147
[28 empty] | 67 | 67 | 72 | 72 | 72 | 72 | 77 | 77 | 77 | 77 | 82 | 82 | 82 | 82 | 87 | 87 | 87 | 87 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92 | 92
[5 empty] | Operator | 8417.6914 | NPV (M$) |  | 33.64% | IRR
[5 empty] | SLB | 4568.96 | NPV (M$) |  | 23.94% | IRR
[6 empty] | Time (Years) | 0 | 0.25 | 0.5 | 0.75 | 1 | 1.25 | 1.5 | 1.75 | 2 | 2.25 | 2.5 | 2.75 | 3 | 3.25 | 3.5 | 3.75 | 4 | 4.25 | 4.5 | 4.75 | 5 | 5.25 | 5.5 | 5.75 | 6 | 6.25 | 6.5 | 6.75 | 7 | 7.25 | 7.5 | 7.75 | 8 | 8.25 | 8.5 | 8.75 | 9 | 9.25 | 9.5 | 9.75 | 10 | 10.25 | 10.5 | 10.75 | 11 | 11.25 | 11.5 | 11.75 | 12 | 12.25 | 12.5 | 12.75 | 13 | 13.25 | 13.5 | 13.75 | 14 | 14.25 | 14.5 | 14.75 | 15 | 15.25 | 15.5 | 15.75 | 16 | 16.25 | 16.5 | 16.75 | 17 | 17.25 | 17.5 | 17.75 | 18 | 18.25 | 18.5 | 18.75 | 19 | 19.25 | 19.5 | 19.75 | 20 | 20.25 | 20.5 | 20.75 | 21 | 21.25 | 21.5 | 21.75 | 22 | 22.25 | 22.5 | 22.75 | 23 | 23.25 | 23.5 | 23.75 | 24
[6 empty] | Well Rate (bpd) | 0 | 15000 | 14550 | 14113.5 | 13690.095 | 13279.3921 | 12881.0104 | 12494.5801 | 12119.7427 | 11756.1504 | 11403.4659 | 11061.3619 | 10729.521 | 10407.6354 | 10095.4064 | 9792.5442 | 9498.7678 | 9213.8048 | 8937.3907 | 8669.2689 | 8409.1909 | 8156.9151 | 7912.2077 | 7674.8415 | 7444.5962 | 7221.2583 | 7004.6206 | 6794.482 | 6590.6475 | 6392.9281 | 6201.1402 | 6015.106 | 5834.6528 | 5659.6133 | 5489.8249 | 5325.1301 | 5165.3762 | 5010.4149 | 4860.1025 | 4714.2994 | 4572.8704 | 4435.6843 | 4302.6138 | 4173.5354 | 4048.3293 | 3926.8794 | 3809.073 | 3694.8009 | 3583.9568 | 3476.4381 | 3372.145 | 3270.9806 | 3172.8512 | 3077.6657 | 2985.3357 | 2895.7756 | 2808.9024 | 2724.6353 | 2642.8962 | 2563.6093 | 2486.7011 | 2412.1 | 2339.737 | 2269.5449 | 2201.4586 | 2135.4148 | 2071.3524 | 2009.2118 | 1948.9354 | 1890.4674 | 1833.7534 | 1778.7408 | 1725.3785 | 1673.6172 | 1623.4087 | 1574.7064 | 1527.4652 | 1481.6413 | 1437.192 | 1394.0763 | 1352.254 | 1311.6864 | 1272.3358 | 1234.1657 | 1197.1407 | 1161.2265 | 1126.3897 | 1092.598 | 1059.8201 | 1028.0255 | 997.1847 | 967.2692 | 938.2511 | 910.1036 | 882.8004 | 856.3164 | 830.6269
[71 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
[72 empty] | -306 | -459 | -688.5 |  |  |  | -1266.5
[5 empty] | O | 0 | -76.5 | -76.5 | 0 | 0 | 0 | -76.5 | -76.5 | 0 | 0 | -76.5 | -76.5 | -76.5 | -76.5 | -76.5 | 0 | -144.5 | -144.5 | -144.5 | -144.5 | -103.5 | -103.5 | -5.5491 | -7.8999 | 78.7566 | 87.1665 | 176.6374 | 169.9141 | 256.3031 | 243.5479 | 341.9536 | 340.2628 | 329.8285 | 319.6446 | 309.7051 | 300.0042 | 290.5361 | 281.2952 | 272.2761 | 263.4735 | 151.3821 | 240.9479 | 230.4132 | 318.0822 | 296.6962 | 391.5584 | 377.409 | 363.5992 | 439.0718 | 427.566 | 417.4325 | 509.613 | 510.8463 | 494.482 | 478.5104 | 462.9222 | 447.708 | 432.8591 | 418.3664 | 404.2216 | 390.4163 | 376.9423 | 363.7917 | 350.9567 | 338.4298 | 326.2034 | 314.2706 | 302.6241 | 291.2571 | 280.1629 | 269.335 | 258.767 | 248.4526 | 238.3857 | 228.5604 | 218.971 | 209.6117 | 200.477 | 191.5616 | 182.8601 | 174.3674 | 166.0786 | 157.9887 | 150.093 | 142.3868 | 134.8655 | 127.5247 | 120.3601 | 113.3675 | 106.5427 | 99.8816 | 93.3805 | 87.0353 | 80.8425 | 74.7983 | 68.8991
[6 empty] | -4 | -1 | -1 | -18 | -18 | -36 | -148 | -120 | -120 | -120 | -120 | -120 | -120 | -120 | -120 | -120 | 60.5 | 60.5 | 60.5 | 60.5 | 85.5 | 85.5 | 90.3263 | 90.1815 | 94.8673 | 66.5863 | -18.8601 | -1.2693 | -1.6662 | 2.775 | 2.2568 | 1.7541 | 6.0927 | 5.4749 | 4.8757 | 9.1207 | 168.912 | 168.2247 | 172.3842 | 171.5927 | 195.8249 | 199.9064 | 199.0392 | 198.198 | 202.2083 | 201.2721 | 200.3639 | 204.3092 | 203.31 | 202.3407 | 201.4004 | 200.4884 | 199.6038 | 198.7457 | 197.9133 | 197.1059 | 196.3227 | 195.563 | 194.8261 | 194.1114 | 193.418 | 192.7455 | 192.0931 | 191.4603 | 190.8465 | 190.2511 | 189.6736 | 189.1134 | 188.57 | 188.0429 | 187.5316 | 187.0356 | 186.5546 | 186.0879 | 185.6353 | 185.1962 | 184.7704 | 184.3572 | 183.9565 | 183.5678 | 183.1908 | 182.8251 | 182.4703 | 182.1262 | 181.7924 | 181.4687 | 181.1546 | 180.85 | 180.5545 | 180.2678 | 179.9898 | 179.7201 | 179.4585 | 179.2047 | 178.9586 | 178.7198
[6 empty] | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040
[5 empty] | Operator | -153 | -153 | -153 | -374 | -578 | -220.4489 | 512.4747 | 1182.0674 | 1259.1823 | 1107.5809 | 940.8254 | 1429.2629 | 1793.6833 | 1946.7609 | 1703.1552 | 1482.1071 | 1281.5278 | 1099.522 | 934.3697 | 784.5103 | 648.5278 | 525.1371 | 413.1723 | 311.5752
[5 empty] | SLB | -24 | -322 | -480 | -419.5 | 242 | 351.5077 | 141.3241 | 5.1197 | 25.564 | 681.1136 | 792.9685 | 808.1536 | 807.5395 | 793.3686 | 780.8233 | 769.717 | 759.8846 | 751.1801 | 743.4741 | 736.652 | 730.6124 | 725.2656 | 720.5322 | 716.3417
Note on C3: LuisMendoza: Do not include in the economics
Note on M5: Roy Shilling: 90 days x 1MM for 15K MODU
Note on N5: Roy Shilling: 90 days x 1MM for 15K MODU
Note on O5: Roy Shilling: 90 days x 1MM for 15K MODU
Note on P5: Roy Shilling: 90 days x 1MM for 15K MODU
Note on M38: Roy Shilling: 90 days x 1MM for 15K MODU
Note on N38: Roy Shilling: 90 days x 1MM for 15K MODU
Note on O38: Roy Shilling: 90 days x 1MM for 15K MODU

## Sheet1
| 1 | 2 | 3 | 4 | 5 | 6 | 7
Frontier Production System
FEED
Detailed Engineering
Procure, Fab and Delivery
Install, Commission Facility
Purpose Built Semi and 20K Subsea
FEED
Detailed Engineering
Procure, Fab and Delivery
Install, Commission Facility